ToR: Short-Term Expert in Communication and Dissemination for the Extractive Industries Transparency Initiative (EITI), Angola

Job title: 	Short-Term Expert in Communication and Dissemination for the EITI in Angola

Project name:   	AGEPI - Apoio à Gestão das Finanças Públicas, das Empresas Públicas, Parcerias

Público-Privadas (PPP) e Inclusão Financeira em Angola (Public Finance Management and the financial sector)

Donor:		European Union

Duration: 	30 working days

Location:             Luanda, Angola

- BACKGROUND:

Angola is the seventh largest country in Africa, with a population, which is forecasted to double within the next two decades. After overcoming a tumultuous recent history, with the end of the colonial time and the civil war in late twentieth century, the country is now on a trajectory of stability and have known its first democratic elections in 2017.

Despite being the sixth-largest economy in Africa, Angola grapples with heavy reliance on oil exports, resulting in economic vulnerabilities. Recent reforms and economic consolidation measures have triggered a growth rebound, but diversification efforts are imperative to reduce oil dependence and address rising inequalities. This goes along with a need to ensure inclusive growth, with better redistribution of the oil industry revenues, significant investments in human capital development and higher education in order to foster a strong diversified economy. The country is highly exposed to challenges related to climate stress, the preservation of environment and the transition to a low-carbon economy.

Angola has been implementing policies to promote inclusive and more equal growth, in the sense to be able to redistribute better the dividends of oil exploitation to the entire population. Some measures were implemented to enhance the perception of the country and business climate, some of which have been achieved despite their rather ambitious character. For instance, the fight against corruption was one of the first priorities of J. Lourenço since his arrival in power. Angola's formal inclusion in the Extractive Industries Transparency Initiative (EITI) in June 2022 is anticipated to enhance transparency and accountability in the oil and gas sector, potentially leading to improved governance and practices.

This project proposes a comprehensive strategy to address key issues in Public Finance Management (PFM) and the financial sector, aligned with the government's priorities and with other initiatives from international partners. Indeed, the Expertise France will design activities ensuring consistency and continuity with an on-going Technical Assistance project financed by the Agence Française de Développement (AFD).

Key beneficiaries include the Ministry of Finance, relevant directorates and public institutions involved in PFM, SOE governance, and PPP implementation.

- DESCRIPTION OF THE MISSION:

Provide strategic and operational support to strengthen communication, dissemination, and stakeholder engagement capacities of the EITI Angola Secretariat.

Key Responsibilities:

- Identify and analyse learning needs and design and implement training plans to strengthen the EITI Secretariat Staff information dissemination capacities;

- Train EITI Staff to develop content (for their website and other relevant social media pages);

- Analyse stakeholders, propose the design and implement stakeholder engagement activities;

- Assist in creating and implementing a comprehensive communication strategy and stakeholder engagement plan;

- Enable EITI Secretariat to organize events with different and relevant stakeholders;

- Support the production of summary reports of the current available reports (the EITI Report Angola 2021 and 2022);

- Coordinate with media and civil society organizations to increase the visibility of EITI activities;

- Support the efforts of the EITI Secretariat by proposing a yearly calendar of dissemination activities.

- Scope of Work

The Expert shall:

- Assess current communication practices and stakeholder engagement;

- Develop a communication and dissemination strategy;

- Design and deliver training sessions to EITI Secretariat staff;

- Support production of communication content (reports, summaries, digital content);

- Propose and structure stakeholder engagement activities;

- Develop an annual dissemination plan.

- Deliverables and Timeline

| Deliverable | Description | Deadline | Indicative Working Days |
| --- | --- | --- | --- |
| D1 – Inception Report | Methodology, work plan, stakeholder mapping | Day 5 | 4 days |
| D2 – Communication Strategy | Strategy including key messages, channels, audiences | Day 15 | 10 days |
| D3 – Training Delivery | At least 2 training sessions and materials | Day 25 | 6 days |
| D4 – Dissemination Outputs | Summary reports and content | Day 25 | 5 days |
| D5 – Final Report | Consolidated outputs and recommendations | Day 30 | 5 days |

The distribution of working days is indicative and may be adjusted by the Expert, provided that all deliverables are completed within the overall timeframe.

All deliverables shall be submitted in English. The Expert shall ensure the provision of a Portuguese translation of all deliverables. Both versions shall be of equivalent quality and suitable for official use and dissemination.

- Reporting and Coordination

The Expert will report to:

- EITI Angola Secretariat

- Expertise France Project Team

- Payment Modality

The contract will be a lump-sum contract. The financial offer shall be provided by the candidate as a total amount covering all costs related to the assignment. Payments will be made upon validation of the deliverables.

Financial conditions may be discussed and finalized during the negotiation phase with the selected candidate.

- PROFESSIONAL EXPERIENCE AND QUALIFICATIONS

- Higher education diploma in Communications, Journalism, Media Studies, Public Relations, Strategic Communication, Digital Marketing, or a related field;

- Minimum of 5 years of professional experience in this field particularly in communication and public outreach, preferably in development cooperation or public sector projects;

- Field experiences on the African continent, particularly in Austral Africa and Lusophone countries will be appreciated;

- Experience in projects with a similar theme: enhanced transparency (in the extractive sector is a plus);

- Knowledge of cooperation mechanisms, donor-funded projects, public development assistance, international cooperation actors;

- Familiarity with EITI principles and standards is an added advantage;

- Previous work with Expertise France, the European Union, or similar international institutions is highly desirable.

- REQUIRED SKILLS AND ASSETS:

- Strong strategic thinking and ability to tailor messages to diverse audiences (government, media, civil society, private sector);

- Exceptional written and oral communication skills coupled with excellent active listening skills.

- Excellent command of Portuguese and English.

- Command of French would be an asset.

- Ability to work effectively in a multicultural/multinational environment.

- Excellent planning and reporting skills.

- Documents and information to provide:

Applications must be sent on the application platform with:

- CV;

- Cover letter.