“Gender mainstreaming in public policy and budgeting”

Terms of reference: Gender Responsive Budgeting EXPERT

1.	Project context

Expertise France is implementing a technical assistance project in several European Union Member States to foster the integration of gender mainstreaming into public policies and budgeting. The project aims to support institutions at central and decentralised level to strengthen the integration of gender into public action though the application of Gender Mainstreaming tools such as Gender Budgeting (GB), Gender Action Plan (GAP) or Gender Impact Assessment (GIA).

The project is articulated in three component:

- Component 1: Analysing the practices and confirming specific needs of each beneficiary authority in order to strengthen the integration of GM, through the application of GM tools such as GB, GAPs or GIA

- Component 2: Operationalization: Capacity building and implementation of GB, GIA or GAP tools;

- Component 3: Capitalisation: Embedding the new practices and enabling their duplication across institutions.

Launched in 2022, the project is now entering its final phase, with a particular focus on Components 2 and 3. Over the past three years, two cohorts of Beneficiary Authorities (BA) have requested tailored technical assistance:

- Eight authorities in Cohort 1, beginning in 2022 and now advancing to the capitalisation stage:

- The City of Strasbourg in France;

- The Land of Berlin, in Germany;

- The Land of Hamburg in Germany;

- The Land of Sachsen-Anhalt in Germany;

- The Commission for Citizenship and Gender Equality in Portugal;

- The Department of Children, Disability, and Equality in Ireland;

- The National Agency for Equal Opportunities Between Women and Men in Romania;

- And the General Secretariat for Equality and Human Rights in Greece at central level.

- And three authorities in Cohort 2, joining in 2024 and currently engaged in implementation:

- The General Secretariat for Equality and Human Rights in Greece, to support the local and regional level;

- The Ministry of Economy and Finance in Italy;

- The Ministry of Finance in Cyprus.

Across both cohorts, each Beneficiary Authority has followed the same sequence: initial analysis, implementation of recommendations and action plans, and consolidation of results and lessons learned.

Component 2: Operationalization: Capacity building and implementation of GB, GIA or GAP tools;

Several field missions will be organised to provide tailored support to the three beneficiary authorities of Cohort 2:

The focus and activities will be guided by the Action Plan (output of A.1.4), which has been adapted to the national context and administrative specificities. The expert will work directly with public officials to address the obstacles and capacity-building needs identified during the in-depth analysis and validated with each beneficiary authority through their Action Plan.

This component will run for approximately six months, from January to July 2026.

Component 3: Capitalisation: Embedding the new practices and enabling their duplication across institutions.

This component aims to ensure that the knowledge and practices developed throughout the project are captured and organised in a short, coherent and accessible format.

For each Beneficiary Authority from Cohorts 1 and 2 that benefits from tailored technical assistance, the expert will prepare consolidated technical notes on good practices. These will document the approaches applied under Component 2 (GB, GIA and GAP), the methodologies tested and the main operational lessons identified. These notes will serve as practical reference materials that authorities may use to support internal dissemination and the voluntary continuation or replication of Gender Mainstreaming/Budgeting practices.

The expert will also support each BA of Cohort 2 in the endorsement and validation of these consolidated outputs, ensuring that they accurately reflect the activities implemented and are aligned with institutional contexts. These deliverables will feed into the project’s closing-event outputs and contribute to the presentation of achievements at national or European level.

Component 3 will be implemented in parallel with Component 2 over approximately six months, from January to July 2026, with remote technical support provided as needed.

2.	Description of the mission

The Gender Responsive Budgeting Expert will be mobilised to support the deployment of the project and provide technical support adapted to the specificities of each beneficiary.

The expected number of working days is 91 until the deliverables are completed.

Main tasks:

- Technical support with direct accompaniment to the beneficiaries;

- Transversal support for the coordination and definition of the activities;

- Definition of the needs in terms of short term expertise and support for the supervision, coordination and communication with the local experts including their reporting;

- Support for technical progress reporting – especially anticipation of the preparation of the final report

The expected deliverables are:

| Table of deliverables |  |
| --- | --- |
| Deliverables | Delivery frequency |
| Mission reports after each expertise missions to Cohort 2 beneficiary authorities; T0+ 2 weeks after coming | Mission reports after each expertise missions to beneficiary authorities; T0+ 2 weeks after coming |
| Working plan for upcoming missions | 1 month before the activity |
| An analytical report with recommendations and reporting the progress made in each Cohort 2 beneficiary country (including local work compilation). This report aims to support local experts in implementing Action Plans | Trimestrial report |
| Review and input to the production for each Cohort 2 beneficiary authority of GRB tools and trainings | Through the total duration of the project |
| Review and Input to Good Practice Case Studies for the capitalization phase (Cohorts 1 and 2) | Through the total duration of the project |
| Preparation of Consolidated Technical Notes on Good Practices, Endorsement and Closing-Event Outputs for each BA (Cohorts 1 and 2) | Through the total duration of the project |
| Contribution to donor progress report | Semestrial basis |
| Contribution to overall final report of the project until approval | Starting 2 months before the end of the project – to 1 month after the end of the project |

3.	Expected profile

- Master's degree or equivalent in political science, economics, international cooperation or equivalent;

- Excellent knowledge of Gender Responsive budgeting;

- Excellent knowledge on gender equality, gender mainstreaming tools;

- Several experience in technical support to public institutions;

- Experience in organizing training sessions

- Excellent ability to work in English (oral and written);

- Excellent command of the language of the country of assignment (oral and written);

- Writing and synthesis skills;

- Good knowledge of office software (Pack Office, Outlook, Internet), particularly Excel;

- Sense of organisation and rigour;

- Sense of diplomacy and ability to adapt;

- Reactivity, autonomy;

- Ability to work in a team.