Expertise France in Libya

Terms of Reference

Senior National Expert – Institutional Engagement & Political-Economy Advisor

Public Financial Management Diagnostic and Reform Roadmap

INVEST4LIBYA

NOVEMBER 2025

Executive Summary

|  | Description |
| --- | --- |
| Project Title | INVEST4Libya – Inception Phase Assessment of Libya’s Fiscal, Financial, and MSME Systems |
| Implementing Agency | Expertise France (EF) – under the EU-funded Special Measure Libya 2024 |
| Donor | European Union Delegation to Libya |
| Implementation Period | 6 months (January – June 2026) |
| Estimated Total Working Days | Approx. 30 expert days |
| Team Composition | 1 Senior National Expert – Institutional Engagement & Political-Economy Advisor |
| Mission Base | Tunis and Tripoli, with fieldwork in Libya (security permitting) |
| Main Purpose | To conduct a comprehensive, research-based, and internationally benchmarked diagnostic of Libya’s public financial management (PFM) system, financial-sector governance, and MSME ecosystem — serving as the analytical and strategic foundation for the full implementation of the INVEST4Libya programme. |
| Specific Objectives (SO) | - SO1: Assess Libya’s Public Financial Management (PFM) framework and identify reform priorities. |
| Expected Key Deliverables | - A Stakeholder Engagement Plan and an updated log of institutional contacts and follow-up actions. - Monthly notes on political-economy developments and institutional engagement progress. - Contextual inputs to the PFM Context Note and to draft diagnostic findings. - TPC meeting notes summarizing attendance, key points, and agreed actions. - Short feasibility inputs on proposed reform options. - A final summary of national feedback on the diagnostic and roadmap. |
| Validation Mechanism | Tripartite validation involving Expertise France and the Libyan Technical Piloting Committee, with EU Delegation as observer. Three formal validation milestones: Inception, Mid-Mission, and Final. |
| Coordination | EF Programme Manager, supported by the Head of Programmes, Deputy Head of Programmes, and the DMEAL & Programme Quality Manager. |

Purpose and Strategic Context

  - General Background

Expertise France is the French public agency for international development cooperation. It is a subsidiary of the Agence Française de Développement (AFD) Group and the second-largest agency of its kind in Europe. Our mission: to strengthen public policies in our partner countries in a sustainable way. Working alongside public actors, civil society, and the private sector, we design and implement projects that stimulate innovation and reinforce their actions to benefit everyone. Through our expertise in governance, security, climate, health, education, entrepreneurship, cultural and creative industries etc., Expertise France contributes to achieving the Sustainable Development Goals (SDGs) in over 140 countries, with public funding from French and European sources.

Since 2016, Expertise France has supported Libya’s economic recovery by empowering the private sector, digitalizing economic services, facilitating access to finance, supporting economic policy reforms, and fostering employability through the reinforcement of skills.

In the area of economic development, the agency contributes to Libya’s diversification and resilience by strengthening private sector capacities, improving access to financial services, accompanying key economic reforms, and enhancing the employability of youth and professionals through targeted skills development.

Regarding digitalization, Expertise France promotes Libya’s digital transformation by advancing digital skills, fostering innovation-led employment opportunities, and supporting the digitization of public services to improve accessibility and efficiency.

In the domain of rule of law, the agency works to reinforce Libya’s democratic institutions by investing in the institutional capacity of key justice stakeholders, strengthening governance mechanisms, and supporting the modernisation of the legal framework.

In the field of health, Expertise France contributes to the improvement of Libya’s healthcare system by supporting national blood transfusion services and implementing robust quality management processes to ensure safety and efficiency.

The INVEST4LIBYA project launch by the European Union aims at supporting libya’s economic institutions to strengthen the diversification of the Libyan economy and the public finance management. The Overall Objective/Impact of this action is the following: Strengthen the Public Finance System and enhance investments for the green and digital transition.

The Specific Objectives (Outcomes) of this action are as follows:

SO 1.	The capacity to design and implement a targeted public financial management reforms is strengthened;

SO 2.	The governance of the financial sector, the legal and regulatory framework for enhancing investments, with a specific focus on the green and digital sectors, is reinforced;

SO 3.	Entrepreneurship, financial inclusion and green and digital innovation are enhanced.

Purpose of the Mission

The inception-phase assessment constitutes the analytical nucleus and strategic inflection point of the INVEST4Libya programme. Its purpose is to subject the project’s entire architecture—its Theory of Change, logical framework, and reform delivery design—to a scientific, methodologically defensible examination anchored in internationally recognised standards.

Over six months (January–June 2026), a senior, multidisciplinary team of experts will conduct a PEFA-informed, IMF- and WBG-aligned diagnostic across Libya’s macro-fiscal, financial-governance, and enterprise-development systems. The assessment’s mandate is not descriptive but determinant: to establish the empirical and institutional foundations upon which all subsequent implementation will rest, and to ensure that every reform measure under INVEST4Libya is credible, feasible, and sequenced within Libya’s political-economy constraints.

Strategic Context

Libya’s reform trajectory stands at a systemic crossroads, defined by structural dependence on hydrocarbons, recurrent fiscal shocks, and the fragmentation of public-sector authority. The volatility of oil revenues, the duplication of institutions, and the erosion of fiscal discipline have created a macro-economic environment where public finance, monetary policy, and investment regulation operate in isolation rather than synergy.

In this context, INVEST4Libya operates as a strategic convergence platform—a mechanism through which fiscal credibility, financial-sector governance, and private-sector dynamism can be realigned into a coherent national development pathway. The inception assessment is therefore conceived not as a baseline study but as a sovereign-scale diagnostic, designed to:

- Identify and prioritise fiscal and financial reforms that can deliver early, confidence-building results without destabilising macroeconomic balances;

- Evaluate institutional interdependencies among the Ministry of Finance (MoF), Central Bank of Libya (CBL), Audit Bureau, Ministry of Economy and Trade (MoE), and Privatisation and Investment Board (PIB)—the limited but decisive set of actors whose coordination determines systemic coherence; and

- Establish the analytical foundations for a sequenced reform roadmap, linking fiscal transparency to financial governance and to the investment ecosystem required for entrepreneurship, innovation, and sustainable growth.

The Stakeholder Network Analysis highlights that reform feasibility in Libya depends less on formal mandates than on institutional alignment and signalling. Progress in one node—budget reliability or payments transparency—reverberates across the system, creating credibility loops that attract investment and consolidate reform momentum. Conversely, failure in a critical institution can cascade through the network, eroding trust and policy traction.

The inception assessment must therefore operate at a strategic altitude: mapping incentives, constraints, and interdependencies with a level of analytical depth comparable to that of IMF Article IV Consultations or World Bank Financial Sector Reviews. It must blend macroeconomic modelling, institutional diagnostics, and applied political-economy analysis into a coherent whole, yielding outputs that can withstand scrutiny by international financial institutions, policymakers, and peer reviewers alike.

Expertise France Strategic Positioning

As the implementing agency and lead technical partner of INVEST4Libya, Expertise France (EF) approaches this inception assessment as a demonstration of methodological excellence and institutional credibility. EF’s ambition is to deliver a diagnostic exercise that meets the highest standards of analytical and academic rigour.

This aspiration reflects EF’s dual identity as both a technical cooperation agency and a centre of methodological innovation within the French Development ecosystem. The Agency’s added value lies in its capacity to integrate:

- International standards with contextual intelligence,

- Empirical analysis with political-economy reasoning, and

- Operational feasibility with academic-grade precision.

Accordingly, the ToRs target only senior, high-calibre experts with demonstrated experience in large-scale fiscal, financial, and institutional reform diagnostics. Entry-level or generalist profiles will not be considered. This mission demands strategic discernment, analytical discipline, and thought leadership commensurate with assignments commissioned by the IMF, the World Bank, or the EU at headquarters level.

EF’s approach to this inception phase is therefore twofold:

- To ensure that the analytical process and deliverables meet the highest international benchmarks of methodological transparency, coherence, and validation; and

- To position EF as a trusted technical interlocutor capable of translating complex reform diagnostics into actionable, nationally owned strategies for Libya’s sustainable economic transformation.

While the European Union remains the donor and contracting authority of the action, this inception mission is entrusted to EF precisely because of the Agency’s proven ability to operate at the intersection of academic rigour and operational diplomacy—a space where few actors can perform credibly in fragile and politically complex contexts.

Strategic Imperative

This inception assessment findings will precise the operational methodology of INVEST4Libya. Its success will:

- Establish the empirical baseline for programme implementation and future evaluations;

- Provide the analytical foundation for adjusting the Description of Action, Theory of Change, and logical framework; and

- will contribute to the enhancement of methodologies and practices underpinning EF-led diagnostics in fragile and transitional environments.

Objectives and scope WorK

The Senior National Expert will provide high-level institutional facilitation, political-economy insight, and strategic engagement to support the inception-phase diagnostic of Libya’s Public Financial Management (PFM) system under INVEST4Libya.

He/She will ensures that the diagnostic is:

- Contextually grounded,

- Politically feasible,

- Institutionally owned, and

- Aligned with Libyan administrative realities.

The expert acts as the primary bridge between Expertise France and Libyan institutions, ensuring access, legitimacy, and contextual intelligence across the entire inception phase.

The Senior National Expert will contribute to the following overarching objectives:

- Enable smooth institutional engagement with Libya’s PFM institutions (MoF, CBL, Audit Bureau, MoP, Parliament).

- Provide political-economy insight essential to interpreting PFM bottlenecks, reform incentives, and institutional dynamics.

- Support the establishment and functioning of the Technical Piloting Committee (TPC), ensuring balanced representation and national ownership.

- Contribute to consultations, validation sessions, and the co-creation of the PFM Reform Roadmap, ensuring recommendations are realistic and implementable.

- Strengthen institutional buy-in, reducing risk of resistance, fragmentation, or misunderstanding.

Given the interlinkages between public finance, financial sector regulation, and private-sector development, the expert will ensure systematic coordination with the inception-phase assessments under SO2 (financial sector strengthening) and SO3 (entrepreneurship and MSME ecosystem), to guarantee methodological coherence and avoid fragmented diagnostics.

More specifically the expert will:

  - Institutional Engagement & Access Facilitation

- Facilitate high-level access to MoF, CBL, Audit Bureau, MoP, Parliament, and relevant directorates.

- Establish relationships with institutional focal points and ensure timely provision of data and documentation.

- Support EF in engaging both Western and Eastern authorities and ensuring balanced participation.

- Mediate institutional sensitivities and reduce risks of misunderstanding or resistance.

- Maintain continuous communication with institutions to ensure alignment with the analytical process.

  - Contextual and Political-Economy Advisory

- Provide political-economy analysis of PFM reforms, incentives, constraints, and institutional interdependencies.

- Inform EF and the international experts of emerging political risks or opportunities that affect timelines or methodology.

- Interpret institutional behaviours, informal practices, and decision-making structures relevant to the diagnostic.

- Validate contextual findings (institutional mapping, workflows, bottlenecks) produced by the international experts.

  - Leadership in the Establishment and Functioning of the Technical Piloting Committee (TPC)

The expert will play a central role in designing, formalizing, and operationalizing the TPC, including:

- Identifying relevant institutions and high-level nominees across Western and Eastern administrations (MoF, CBL, Audit Bureau, Ministry of Planning, Parliament).

- Conducting political groundwork to secure formal institutional endorsement, signatures, and buy-in for TPC membership.

- Facilitating communication with senior officials to obtain nominations from the appropriate level of authority.

- Supporting EF in preparing and delivering letters, invitations, and follow-up correspondence.

- Assist in organising and chairing the inaugural TPC meeting.

- Ensure the TPC becomes a functional, respected mechanism through:

- Regular follow-ups with members

- Tracking commitments and data requests

- Ensuring attendance and participation

- Consolidate TPC feedback during diagnostic and roadmap stages.

  - Contribution to Diagnostics, Consultations & Roadmap Development

- Participate in structured interviews, focus groups, and consultations with institutions.

- Validate and enrich technical findings by adding contextual insights.

- Ensure that sensitive sections of the diagnostic are appropriately framed for Libyan institutional audiences.

- Participate in interim and final validation workshops.

- Provide feasibility assessments on proposed reforms (risks, institutional capacity, political acceptability).

- Facilitate national endorsement of the final diagnostic and reform roadmap.

methodology

The Senior National Expert will apply a methodology that blends political-economy insight, participatory engagement, and evidence-based institutional analysis, consistent with the overall inception phase methodology.

  - Key Methodological Principles

- Context-driven interpretation of findings

- Continuous institutional engagement

- Sensitivity to political and regional dynamics

- Active participation in the EF-led analytical process

- Systematic coordination with the international PFM experts and EF team

- Alignment with SO2 and SO3 where institutional mandates intersect

  - Operational Approach

- Weekly coordination meetings with EF Libya team and the international experts.

- Continuous interface with the TPC throughout the inception phase.

- Joint preparation and participation in national consultations and validation sessions.

- Use of structured templates for engagement logs, political-economy briefs, and TPC follow-up.

Throughout the process, the expert will emphasize capacity transfer by involving Libyan technical counterparts in data collection, analysis, and validation. This ensures the outputs are not only technically sound but also institutionally owned and implementable.

Expected Deliverables

Deliverables

- A Stakeholder Engagement Plan and an updated log of institutional contacts and follow-up actions. - Monthly notes on political-economy developments and institutional engagement progress. - Contextual inputs to the PFM Context Note and to draft diagnostic findings. - TPC meeting notes summarizing attendance, key points, and agreed actions. - Short feasibility inputs on proposed reform options. - A final summary of national feedback on the diagnostic and roadmap.

governance STRUCTURE

Governance Approach

The governance and validation architecture of the inception-phase assessment is designed to balance technical independence with institutional legitimacy. Given the strategic sensitivity of Libya’s fiscal and financial domains, the validation process must ensure that analytical findings are credible, nationally anchored, and internationally defensible.

The governance system rests on three complementary layers:

- Expertise France (EF) – ensuring methodological rigour, operational discipline, and donor compliance;

- Libyan Technical Piloting Committee – ensuring political legitimacy, contextual realism, and national ownership;

- European Union Delegation – ensuring policy alignment, coherence with the EU Special Measure 2024, and donor visibility.

Institutional Configuration

The assessment’s governance structure will operate through a dual-validation mechanism between Expertise France and the Libyan Technical Piloting Committee, supported by structured communication with the EU Delegation and EF Headquarters (Paris).

This configuration ensures that validation is both technically robust and politically grounded, maintaining a clear chain of accountability while preserving EF’s analytical autonomy.

Profile and Expertise Required

The Senior National Expert should bring substantial experience in Libya’s public sector and demonstrate the credibility, networks, and institutional understanding necessary to engage effectively with high-level authorities and support a complex PFM diagnostic process. Minimum requirements include:

Advanced degree (Master’s or PhD) in Public Finance, Economics, Accounting, Public Policy, or related discipline.

At least 15 years of progressively responsible experience in PFM reforms, fiscal transparency, expenditure management, and budget reform.

Strong familiarity with Libyan institutions (Ministry of Finance, Central Bank of Libya, Audit Bureau, Tax & Customs Authority).

Expertise in fiscal governance and its linkages with financial sector regulation and investment climate reforms.

Experience in facilitating structured policy dialogue with government institutions, civil society, and international donors.

Strong knowledge of international PFM best practices and tools, including IMF FAD methodologies, PEFA, and WB frameworks.

Excellent interpersonal and communication skills, with fluency in Arabic and English.

DURATION AND WORKLOAD

The estimated workload for delivering this assignment is 20 man/days, to be implemented over the period January to June 2026..

Ethical Standards, Confidentiality, and Data Protection

All activities undertaken within the framework of this inception-phase mission must strictly adhere to the ethical standards and professional conduct principles established by Expertise France (EF) and the European Union. The expert team shall uphold the highest standards of integrity, impartiality, and accountability, ensuring that no action or decision compromises the credibility, neutrality, or independence of the assessment process.

All experts must maintain strict confidentiality regarding any information, data, or documentation obtained during the course of the mission. This obligation applies to all forms of communication — written, verbal, and digital — and remains in force even after the completion of the assignment.
Sensitive or classified data related to public finance, financial institutions, or national strategies must be handled with particular caution and shared exclusively through channels authorised by Expertise France.

- In accordance with the European Union General Data Protection Regulation (EU-GDPR 2016/679), all data collection, processing, storage, and transmission carried out by the experts shall comply with EU data-protection principles, including lawfulness, purpose limitation, data minimisation, accuracy, integrity, and confidentiality. No personal or institutional data may be reproduced, stored, or transferred to third parties without the prior written authorisation of Expertise France.

All team members must also comply with EF’s internal Code of Ethics, which mandates the prevention of conflicts of interest, non-discrimination, respect for human rights, and the responsible use of information. Any breach of ethical or data-protection obligations will result in immediate contractual sanctions and disqualification.

This mission shall operate under a zero-tolerance policy toward misconduct, ensuring that all actions reflect the integrity and trust that underpin EU-funded cooperation.

REPOrting and Communication Protocols

The expert team will maintain a structured and transparent communication framework with Expertise France (EF) throughout the inception mission. All exchanges, deliverables, and coordination notes must be transmitted in English, the sole working language of this assignment.

  - Reporting Structure

- All official deliverables (reports, notes, briefs, presentations) shall be submitted to the Programme Manager of INVEST4Libya, with copies to the Head of Programmes, Deputy Head of Programmes, and the DMEAL & Programme Quality Manager.

- The expert shall provide:

  - Weekly coordination updates (email or brief memo, 1–2 pages).

  - Bi-weekly technical progress notes, summarising key analytical developments, challenges, and next steps.

  - Formal deliverables according to the timeline in Section 4.

- All meetings with the EU Delegation or Libyan stakeholders must be pre-approved and jointly attended with EF, ensuring unified communication and institutional coherence.

  - Format and Branding

All reports must follow EF’s standard format (Word/PDF, A4, EF and EU logos) and include:

- Cover page with title, mission name, and date;

- Executive summary (max. 2 pages);

- Main body structured by analytical pillar;

- Annexes (data sources, references, validation records).
All outputs must include the following disclaimer:

“This document was produced with the financial support of the European Union. Its contents are the sole responsibility of Expertise France and do not necessarily reflect the views of the European Union.”

  - Confidentiality and Communication Ethics

All public or external communications (including presentations, interviews, or citations) must receive prior written authorisation from Expertise France. No information collected during the mission may be disclosed without EF’s explicit consent.

Administrative and Logistical Arrangements

The inception mission will be managed operationally by Expertise France – Libya Office, with coordination from the Programme Manager and support from the Tunis-based EF support unit.

#### Mission Base and Mobility

The expert team will operate primarily from Tunis and Tripoli, depending on security conditions and access permissions. Short-term missions to Libya will be planned and approved by EF based on feasibility, visa issuance, and safety advisories. Remote collaboration mechanisms will be established when physical presence is not possible.

#### Travel and Security

All international and domestic travel must comply with EF’s security and travel protocols for service providers. Experts will receive a security briefing and clearance prior to deployment in Libya. Travel arrangements, accommodation, and on-ground logistics will be coordinated by EF Libya’s Administration and Operations Unit.

#### Administrative Coordination

EF Libya will facilitate:

- Visa requests and administrative clearances, in coordination with national authorities;

- Office access and local transportation during in-country missions;

#### Working Modalities

Experts are expected to work both on-site and remotely, maintaining continuous communication with EF. All mission costs (travel, accommodation, per diem) will be managed in accordance with EF’s financial regulations and EU contractual procedures.

The expert team must ensure availability, adaptability, and operational discipline to deliver high-quality outputs within the agreed timeline and under EF’s supervision.