TERMS OF REFERENCE
AND TECHNICAL SPECIFICATIONS

I.  General information

| Assignment name | Provision of International Expert Consultation Services on Legislative, Regulatory and Policy Reform of the Penitentiary and Probation Systems in Line with European Standards |
| --- | --- |
| Beneficiary | Ministry of Justice of Ukraine and relevant penitentiary and probation institutions |
| Name of the project and code | PravoJustice4EU, 25GEO0C350 |
| Country | UKRAINE |
| Total estimated number of days | 42 |

II. Context and justification of the need

The PravoJustice4EU Programme, implemented by Expertise France (EF) with funding from the European Union and the French Ministry for Europe and Foreign Affairs, supports Ukrainian authorities in the continued reform and strengthening of the justice sector.

PravoJustice4EU is structured around two specific objectives: supporting the EU accession process by aligning the Ukrainian justice system with EU standards, including independence, efficiency, quality, integrity, transparency and access to justice; and supporting accountability for core international crimes in line with European and international standards while fostering a holistic transitional justice approach.

Under Result 1.7.3, “Penitentiary and probation systems are strengthened in line with European standards”, the Programme supports improvements to policy and regulatory frameworks, professional capacity, institutional arrangements and rehabilitative interventions.

International legal expertise is required to provide comparative European analysis and support the development and improvement of Ukraine’s penitentiary and probation legislation, policies and strategies in line with European standards. Specific assignments and deliverables will be determined in consultation with beneficiaries and in accordance with Programme priorities.

III. Objectives and desired results

1) General objective

To provide international legal and policy expertise supporting the development and improvement of Ukraine’s penitentiary and probation legislative, regulatory and strategic frameworks in accordance with European standards and relevant international human rights obligations.

2) Specific objectives

- Provide comparative legal and policy analysis of European penitentiary and probation systems and identify approaches relevant to the Ukrainian reform context.

- Review priority Ukrainian legislation, draft regulatory documents, strategies and implementation plans and prepare recommendations for their improvement.

- Contribute, in cooperation with national experts and Ukrainian institutions, to the development and revision of priority legislative, regulatory and strategic documents.

- Provide expert consultations, participate in stakeholder discussions and facilitate the transfer of relevant European knowledge and experience.

3) Anticipated results

- Priority legislative, regulatory and strategic documents are reviewed against relevant European and international standards.

- Comparative analyses, legal opinions and actionable recommendations inform the development and revision of penitentiary and probation reform proposals.

- Ukrainian institutions and national experts benefit from targeted international advice and knowledge exchange on relevant European approaches.

IV. Description of the assignment

1) Planned activities

The expert shall perform the following technical activities under the supervision of designated PravoJustice4EU Programme representatives and in consultation with relevant beneficiaries. Specific tasks will be agreed according to Programme priorities:

- Review selected Ukrainian penitentiary and probation policies, strategies and legislation against relevant European standards and comparative European practice; prepare analytical findings and recommendations.

- Provide written legal opinions, comparative analyses and proposed revisions concerning draft laws, secondary regulations, strategies and implementation measures related to penitentiary and probation reform.

- Cooperate with national legal experts and Ukrainian institutions in drafting or revising legislative, regulatory and strategic proposals, including explanatory notes and comparison tables where appropriate.

- Participate in stakeholder consultations and working groups; prepare briefing materials, presentations and targeted knowledge-transfer sessions on European approaches.

The assignment may be delivered through a combination of on-site and remote work, subject to the approved work plan and contractual arrangements.

2) Anticipated deliverables

Deliverables:

D1. Comparative legal and policy analysis. Analytical report reviewing selected Ukrainian legislation, policy or strategic documents against relevant European standards and comparative practices, identifying gaps and providing recommendations.

D2. Legal opinions and drafting contributions. Written legal opinions, proposed amendments, revised draft provisions or contributions to legislative, regulatory and strategic documents, with explanatory notes and/or comparison tables as appropriate.

D3. Expert consultations and knowledge-transfer materials. Expert presentations, briefing notes, consultation materials and documented recommendations prepared for stakeholder consultations, working groups or knowledge-exchange activities.

D4. Consolidated recommendations and technical summary. Consolidated recommendations summarising completed assignments, outstanding legal and policy issues, and proposed follow-up measures for consideration by relevant institutions.

3) Consultation

Experts shall work under the overall supervision of the National Key Expert on Penitentiary Reform and Pillar 1 Lead.

The expert shall work under the overall supervision of PravoJustice4EU Programme management and the relevant thematic lead, in consultation with the National Key Expert on Penitentiary Reform, other Programme experts and designated beneficiary representatives. Draft outputs shall be submitted for review and revised in response to consolidated feedback.

Experts shall promptly communicate any potential conflict of interest, confidentiality concern or other circumstance that may affect the performance of the assignment.

4) Implementation period

Start date: January 2027

End date: June 2030

Effective duration of the assignment: 42 months

5) Place of performance

The assignment shall primarily be performed on a home-based basis. Frequent travel to and within Ukraine may be required, upon formal request by Expertise France and subject to applicable security and contractual arrangements.

Participation in meetings, consultations and other Project activities may take place in person or online, subject to prior agreement with the Program Key Expert.

V.  Required expertise and profile

1) Number of experts per assignment: 1

2) Profile of the designated expert responsible for contract execution

A. Qualifications and skills:

- Advanced university degree (Master’s degree or PhD) in law.

- Excellent comparative legal analysis and drafting skills.

- Strong knowledge of European penitentiary, probation and human-rights standards.

- Ability to communicate complex legal issues to national stakeholders.

- Fluency in English is required.

B. General professional experience

●	At least 5 years of experience in criminal justice, penitentiary or probation law or policy, legal reform or a closely relevant field.

●	Experience advising public institutions and/or international justice-sector reform programmes.

C. Specific professional experience

- Direct experience cooperating with penitentiary or probation institutions or relevant public authorities.

- Demonstrated comparative legal work and review of legislation, strategies or regulations against European standards.

- Experience with joint drafting, consultation and knowledge-transfer activities.

- Previous experience under Pravo-Justice or another EU-funded or internationally supported justice-sector reform programme is an asset.

VI. Assignment reports

The expert shall provide periodic activity and progress reporting in accordance with the contractual modality and Program procedures. This may include monthly or periodic progress reports and timesheets, as applicable, summarizing work performed, tasks completed, documents prepared or reviewed, meetings and consultations attended, outputs produced, issues encountered and proposed next steps. All substantive deliverables shall be submitted to Expertise France for review and acceptance, and consolidated comments shall be addressed within the agreed timeframe.

VII. Monitoring-evaluation

Performance indicators

| Deliverables | Immediate effects | Intermediate effects | Verification sources |
| --- | --- | --- | --- |
| Comparative legal and policy analysis | Gaps between selected Ukrainian legal and policy frameworks and relevant European standards are identified, with substantiated recommendations for improvement. | The Ministry of Justice and relevant institutions have a stronger evidence base for aligning priority reform proposals with European standards. | Comparative analytical report; source references; beneficiary feedback; accepted deliverable. |
| Legal opinions and drafting contributions | Draft legislation, regulatory provisions or strategic proposals are reviewed and improved through international legal analysis and recommendations. | Relevant institutions are better equipped to advance coherent legislative and policy proposals informed by European experience. | Legal opinions; revised draft documents; explanatory notes; comparison tables; review comments. |
| Expert consultations and knowledge-transfer materials | Ukrainian stakeholders receive targeted expert input on European standards and comparative practices, and relevant comments are documented. | Improved understanding of European approaches supports informed stakeholder discussions and more consistent reform proposals. | Consultation agendas; presentations; briefing materials; meeting records; consolidated comments; participant feedback where available. |
| Consolidated recommendations and technical summary | Key findings, outstanding legal and policy issues and recommended follow-up measures are consolidated and documented. | Programme management and beneficiaries have a structured basis for planning subsequent legislative and policy support. | Consolidated recommendations; technical summary; accepted deliverables; beneficiary feedback. |

Experts shall comply with all applicable Expertise France contractual, administrative, security, confidentiality, data-protection, ethics, conflict-of-interest and visibility requirements. Participation in travel, events or activities outside the normal place of performance shall be subject to prior approval and applicable Program procedures.

T Deliverables shall be prepared in English, as agreed for each assignment; translation or interpretation support may be arranged subject to Programme procedures. The level of effort includes preparation, meetings, consultations, analysis, drafting, presentations and revision of outputs.

IX. Evaluation Criteria

Criterion 1: Financial offer / Price (rate per day) – 30 points

The financial score will cover the comparison of the financial offers of all candidates having submitted a conforming proposal.

Criterion 2: Technical offer – 70 points

Technical evaluation (desk review and/or interview based):

| Sub-criterion 1: Education - University degree in Law from an accredited university – 5 points. - Postgraduate degree (Master’s, LL.M., PhD or equivalent) in Law, European law, international human rights law or another relevant field – 5 points. | 10 |
| --- | --- |
| Sub-criterion 2: Experience - At least 5 years of professional experience in criminal justice, penitentiary or probation law or policy, legal reform or a closely relevant field – 10 points. - Demonstrated experience in comparative legal analysis and assessment of penitentiary and probation legislation, policies or strategies against European and international standards – 10 points. - Experience in drafting or reviewing legislative, regulatory, strategic or analytical documents related to penitentiary and probation reform – 5 points. - Experience in stakeholder consultation, expert working groups, professional training or knowledge-transfer activities – 5 points. - Previous experience under Pravo-Justice or another EU-funded or internationally supported justice-sector reform programme in Ukraine – 5 points. | 35 |
| Sub-criterion 3: Technical Knowledge & Skills - Understanding of the assignment, with all relevant components of the ToR identified and addressed – 22 points: - Excellent – 22 points - Good – 20 points - Satisfactory – 15 points - Poor – 9 points - Very poor – 2 points - Full professional proficiency in written and spoken English – 2 points. - Working knowledge of Ukrainian – 1 point. | 25 |
| Total | 70 |

Each technical offer, deemed to be technically conforming, will be attributed a technical score.  By adding up the weighted scores obtained for each sub-criterion.

Where the contracting modality provides for a financial offer, the weighting between the technical and financial evaluation shall be specified in the call for applications.

X.  Submission Details

The candidate should provide:

•  Updated CV demonstrating compliance with the required expertise and profile.

•  Financial offer / proposed daily rate, where applicable to the contracting modality.

•  The selected candidate will be requested to provide additional supporting documentation requested for evaluation, due diligence, or contracting purposes.