Terms of reference

for the recruitment of external consultants for the final evaluation of the 'Basketball Experience' project

Estimated start date for the Final evaluation: February 2026.

GENERAL INFORMATION

| Field | Information |
| --- | --- |
| Title of the mission | Final Evaluation of the Basketball Experience (BE) Project |
| Beneficiary(s) | Expertise France |
| Country | Kenya |
| Estimated duration of the evaluation | 45 person-days |
| Donor | French Development Agency (AFD) |
| Period covered by the evaluation | July 2024 – December 2026 |

# ACRONYMS

| Acronym | Full Meaning |
| --- | --- |
| BE | Basketball Experience |
| BE-DI | Basketball Experience – Disability Inclusion |
| KRCS | Kenya Red Cross Society |
| EF | Expertise France |
| NBA Africa | National Basketball Association Africa |
| AFD | Agence Française de Développement (French Development Agency) |
| MoE | Ministry of Education |
| KAS | Kenya Academy of Sports |
| PE | Physical Education |
| DPO | Disabled Persons Organization |
| MEAL | Monitoring, Evaluation, Accountability and Learning |

TABLE OF CONTENT

ACRONYMS	2

1	BACKGROUND AND CONTEXT OF THE BASKETBALL EXPERIENCE (BE) PROGRAMME IN KENYA	5

1.1	PROGRAMME RATIONALE AND VISION	5

1.2	PROGRAM BUDGET	6

1.3	TARGETS REACHED IN KENYA (2024–2025)	6

1.4	SUMMARY OF MID-TERM EVALUATION FINDINGS	7

1.5	KEY RECOMMENDATIONS FROM THE MID-TERM EVALUATION	7

2	SUMMARY PRESENTATION OF THE BASKETBALL EXPERIENCE PROGRAM IN KENYA	8

2.1	THE BASKETBALL EXPERIENCE (BE) PROGRAM IN KENYA	8

2.2	DISABILITY INCLUSION COMPONENT (BE-DI)	9

2.3	IMPLEMENTATION DATES	9

2.4	LOCATIONS OF INTERVENTION	9

2.4.1	Nairobi County	10

2.4.2	Kiambu County	10

2.4.3	Kajiado County	10

2.4.4	Machakos County	10

2.5	OPERATIONAL PARTNERS IN KENYA	10

2.6	COORDINATION SYSTEM	11

2.7	TARGET GROUPS	11

2.7.1	Primary Target Groups	11

2.7.2	Secondary Target Groups	11

3	PROJECT COMPONENTS (KENYA – BE AND BE-DI)	12

Component 1: Development of Local Sports Infrastructure	12

Component 1.1 Construction and Rehabilitation of Basketball Courts	12

Component 1.2 Court Management, Maintenance, and Animation	12

Achievements of Component 1 (Kenya)	12

Component 2: Implementation of Socio-Educational and Inclusive Sports Programs	12

Component 2.1 Development of Socio-Educational Content & Capacity Building	12

A. Co-Construction of Inclusive Educational Content	12

B. Training of Coaches, Teachers, and Inclusive Sports Personnel	12

Component 2.2 Delivery of Inclusive Education and Awareness Activities	13

I. Assemblies (Introductory Sensitization)	13

II. Clinics (Weekly Life Skills + Basketball Sessions)	13

III. Annual Basketball Experience Kenya Inclusive Tournament	13

Component 3: Project Management, Communication, and Capitalization	13

Component 3.1 Project Management, Audits, and External Evaluations	13

Component 3.2 Communication	13

Component 3.3 Capitalization and Legacy Development	13

4	OBJECTIVES OF THE ASSIGNMENT	14

4.1	Rationale for the final evaluation (Kenya BE and BE-DI Projects)	14

4.2	MAIN OBJECTIVE	14

4.3	SCOPE OF WORK	15

5	CRITERIA AND EVALUATIVE QUESTIONS	16

5.1	EVALUATION CRITERIA AND SPECIFIC EVALUATIVE QUESTIONS (KENYA BE AND BE-DI FINAL EVALUATION)	16

6	DESCRIPTION OF THE MISSION (KENYA FINAL EVALUATION ADAPTATION)	19

6.1	METHODOLOGY ADOPTED	19

6.2	PROCESS	19

6.3	START-UP PHASE	19

6.4	DATA COLLECTION PHASE	20

6.5	REPORTING PHASE	21

6.6	EXPECTED DELIVERABLES AND TIMELINE	21

7	ORGANIZATION OF WORK (KENYA FINAL EVALUATION ADAPTATION)	21

7.1.1	Management and Governance	22

7.2	COORDINATION ARRANGEMENTS	22

7.3	ORGANIZATION OF FIELD MISSIONS	22

7.4	Indicative Timetables	22

7.5	REQUIRED QUALIFICATIONS AND PROFESSIONAL PROFILES	23

7.5.1	Lead Evaluators	23

7.5.2	Expert, Head of Mission	23

a)	Expert	23

b)	Additional Requirements	24

7.6	PROPOSAL SUBMISSION REQUIREMENTS	24

7.7	EVALUATION AND SELECTION CRITERIA	24

1. Technical Offer	24

Criterion 1: Understanding of the Terms of Reference and Objectives	25

Criterion 2: Methodological Approach and Quality Assurance	25

Criterion 3: Organization of Tasks and Timeline	25

Criterion 4: Experience and Qualifications of the Evaluation Team	25

2. Financial Offer	25

8	ANNEXES	26

# BACKGROUND AND CONTEXT OF THE BASKETBALL EXPERIENCE (BE) PROGRAMME IN KENYA

The Basketball Experience (BE) programme is a multi-country initiative that uses basketball as a vehicle for education, personal growth, and social inclusion among school-aged children. Funded by the Agence Française de Développement (AFD) and implemented in partnership with NBA Africa, Expertise France, the Kenya Red Cross Society (KRCS), Admedia, the Ministry of Education (MoE), and the Kenya Academy of Sports (KAS), the programme seeks to create safe and dynamic learning spaces where children can build confidence, discipline, resilience, and leadership skills through sport.

Kenya officially joined the BE network in 2024, following successful implementation in Morocco and Nigeria. The programme commenced with the onboarding of schools, the training of coaches, and the inauguration of an NBA-standard basketball court in Nairobi. Since then, implementation has expanded across multiple counties, engaging thousands of learners through assemblies, clinics, and school-based events. Schools have embraced BE as a transformative initiative, noting that basketball courts have evolved into vibrant environments where learners express themselves, develop character, and build meaningful relationships.

The Kenyan rollout was guided by lessons from earlier phases of the Programme, including the importance of combining sport with structured life skills learning. Evidence from Kenya shows that participation in sporting activities can have a significant positive influence on learners’ academic performance (Mutuma, 2023), while structured models of sport education have been shown to enhance motivation, cognitive development, and social skills (Araújo et al., 2024). With strong demand from teachers, communities, and learners, national experiences in Kenya also highlight the importance of teacher capacity and institutional support in sustaining participation (Ong’ang’a, 2022). This strong foundation, alongside established examples of disability-inclusive sports initiatives such as the Kenyatta University Disability Sports Association (Ngunjiri, 2012), supports the introduction of the Disability Inclusion (BE-DI) component, which is planned to begin in 2026.

## PROGRAMME RATIONALE AND VISION

The rationale behind the BE programme in Kenya is rooted in the belief that sport, when intentionally structured, is a powerful tool for cultivating essential life skills and strengthening positive youth development. Children between the ages of 10 and 17 are at a formative stage where confidence, identity, emotional intelligence, and social values take shape. The BE programme enables learners to strengthen these competencies in a supportive, fun, and socially engaging environment.

Basketball is used not only as a physical activity but as a platform for teaching teamwork, communication, discipline, respect, and resilience. Coaches are trained to serve as mentors who guide children through both sport-related and personal challenges. The objective is to integrate life skills, teamwork, and gender equality in teaching practices, in order to help improve students’ social emotional skills, collaboration abilities, and awareness of equality and inclusion.

The BE vision goes beyond improving sports performance. It aims to strengthen wellbeing, promote gender equity, support inclusion, and enhance the overall learning experience for young people. This vision is expanding further with the introduction of the BE Disability Inclusion (BE-DI) Phase, which will ensure that children with disabilities especially those with physical, hearing, and visual impairments are able to participate fully in sports and life-skills activities.

Importantly, both the original BE component and the BE-DI disability component will be implemented concurrently in 2026, allowing the programme to deepen its existing work in mainstream schools while simultaneously building inclusive models that respond to the needs of diverse learners.This dual implementation approach strengthens the BE programme’s positioning as a notable example of inclusive, skills-based education delivered through sport in Kenya.

## PROGRAM BUDGET

The total programme budget for the Basketball Experience (BE) programme in the context of Kenya is set to be EUR 770,000 within the duration of 2024-2026 comprising the Classic BE component and the Disability Inclusion (BE-DI) component. This budget is expected to contribute to the effectiveness and sustainability of the programme.

Basketball Experience (BE) Classic Component is granted EUR 420,000. It includes activities involving core implementation, such as on-boarding in schools, training coaches, conducting sessions on basketball as well as life skills, events at schools and at national levels, safeguarding, as well as overall coordination.

The BE Disability Inclusion (BE-DI) Component receives an allocation of EUR 350,000 to support the Scaling Up Inclusive Sports Programming from 2026. This amount will go towards support for specialized coach and staff capacity building, modified sports equipment and infrastructure, and enhanced monitoring mechanisms.

Taken collectively, these allocations of budget provide for the necessary resources to ensure that the high-quality and sustainable Basketball Experience program is offered in Kenya. This will enable the conduct of inclusive educational-through-sport activities that develop life skills and ensure that both the mainstream and disability inclusive parts of the program have lasting impacts

## TARGETS REACHED IN KENYA (2024–2025)

During its first year of implementation, the BE programme in Kenya registered notable progress by reaching a wide range of beneficiaries across schools and communities. By the end of 2025, the programme had engaged 52,953 children through various activities. Of these, 50,934 learners were reached through school assemblies that introduced life-skills themes, while 1,667 learners participated in structured basketball clinics that combined technical training with hands-on life-skills learning. Additionally, 352 learners took part in the national Final Game event, including 30 children with disabilities, making a step toward inclusive participation.

The programme also recorded strong participation in regular clinic sessions, where 1,990 learners were engaged more intensively. This group included 1,032 boys without disabilities, 862 girls without disabilities, and 96 children with disabilities who joined general activities. These early experiences provided critical insights into the barriers faced by learners with disabilities and helped shape the design of the upcoming BE-DI phase.

Capacity building was another key achievement. A total of 19 coaches were trained by mid-2024, followed by 20 additional coaches later in the year. The training delivered jointly by NBA Africa and KRCS covered technical basketball skills, safeguarding, psychosocial support, and facilitation of life-skills sessions. This has created a strong pool of youth mentors capable of delivering high-quality socio-sport activities across schools. By 2025, the BE programme was actively working with 48 schools, with plans to onboard an additional 48 new schools in 2026. This expansion, together with the concurrent rollout of the disability inclusion component, demonstrates the programme’s growing national footprint and its unique value in Kenya’s education and child development landscape.

## SUMMARY OF MID-TERM EVALUATION FINDINGS

In 2024, an external mid-term evaluation was conducted for BE program, focusing on the first two countries of implementation: Morocco and Nigeria. The Mid-Term Evaluation concludes that the Basketball Experience program is highly relevant and resonates with schools, communities, and young participants due to its innovative use of sports as a vehicle for psychosocial and life-skills development. This program effectively enhanced foundational competencies like self-confidence, communication, teamwork, and emotion management-competencies consistently observed across both Moroccan and Nigerian sites. Its pedagogical dimension, however, needed more depth, particularly in the delivery of more complex social and civic topics such as gender equality, good citizenship, respect for diversity, and peaceful coexistence, which was not fully possible due to limited involvement of teachers, inconsistent integration of an educational content into the school routine, and partial preparedness of the coaches to manage sensitive discussions. The program also demonstrated some persistent challenges in ensuring equal and inclusive participation among targeted beneficiaries. Most spots were taken by boys who already practiced sports, whereas girls’ participation was limited by cultural norms, lower prior exposure to sports, and family prohibition. Sustainability was identified as one of the weakest points: program activities were not deeply rooted in institutional frameworks, the renovated playgrounds were underutilized for structured educational purposes, and few opportunities were provided for continued basketball practice and for coaches’ professional development. Despite high participation rates, significant media visibility, and excellent infrastructure investments, poor coordination with local systems, weak ownership of the programs by education authorities, and financial barriers to continued practice of sports drastically reduced broader and longer-term impact of the program, calling for stronger partnerships, better targeting, and more robust capacity-building strategies.

## KEY RECOMMENDATIONS FROM THE MID-TERM EVALUATION

The mid-term evaluation issued nine recommendations to guide the 2024–2026 program cycle. Under Pillar 1: Leadership of Local Partnerships and Project Monitoring, the evaluators recommend strengthening collaboration with institutional and educational partners through their early involvement in steering committees, the co-construction of educational content, and proactive sustainability planning. They further advise refining the monitoring system by collecting data disaggregated by age, sex, and gender; ensuring data is available in disaggregated formats; tracking individual student participation over time; and systematically documenting the frequency with which each life-skills theme is delivered.

Under Pillar 2: Strengthening the Educational and Life-Skills Dimension, the evaluation recommends diversifying the profiles of recruited professionals by engaging individuals from complementary backgrounds, including educators, teachers, social workers, youth facilitators, and community-based practitioners. It also calls for strengthening coaches’ training in pedagogical approaches and involving thematic experts in key areas such as gender, citizenship, and health. Additional recommendations include enriching cultural and social activities, investing in playgrounds to transform them into dynamic education-through-sport spaces, and refining target groups by focusing on pupils of similar academic levels, with particular emphasis on younger learners, especially those in primary schools.

Recommendations under Pillar 3: Sustainability and Continuity of Program Activities emphasize the importance of long-term impact. These include supporting coaches in their professional transition following their involvement in the program and encouraging local organizations to integrate the Basketball Experience pedagogical approach into their own structures. This can be achieved through the development of transferable training materials and increased involvement of local actors in training sessions, thereby strengthening local ownership and sustainability.

# SUMMARY PRESENTATION OF THE BASKETBALL EXPERIENCE PROGRAM IN KENYA

## THE BASKETBALL EXPERIENCE (BE) PROGRAM IN KENYA

The Basketball Experience (BE) program is designed as a structured, school-based sports and life-skills initiative targeting children and adolescents in Kenyan primary and secondary schools. Built upon the philosophy that sports can be an effective medium for education, behavior change, and social cohesion, BE integrates weekly basketball sessions with age-appropriate life skills modules. These modules cover themes such as communication, teamwork, leadership, respect, gender equality, conflict resolution, resilience, and personal development.

Implementation began in 2024, following a series of strategic planning and coordination meetings with NBA Africa, AFD, Expertise France, the Ministry of Education, Kenya Academy of Sports (KAS), and Admedia. The first year of BE emphasized operational readiness: recruiting and training coaches, establishing school partnerships, designing communications materials, and developing a robust program launch.

The program’s approach is as follows: 20 coaches receive technical basketball training from NBA Africa, while KRCS delivers comprehensive training on life skills, safeguarding, child protection, and inclusive facilitation techniques. The program’s visibility is enhanced through carefully orchestrated events such as the inaugural court launch, the first coach training sessions, and ongoing engagement activities in participating schools. By positioning basketball as an accessible and engaging sport, BE nurtures youth participation regardless of background and ensures that life skills messages are reinforced through repeated practice, role modeling, and applied learning during weekly clinics.

## DISABILITY INCLUSION COMPONENT (BE-DI)

The Disability Inclusion component introduces an innovative expansion to the BE framework. Recognizing that learners with disabilities face disproportionate exclusion from sports, BE-DI tailors its interventions to address the distinct needs of children with visual, hearing, and physical/mobility impairments. This includes:

- Tailored coaching techniques that accommodate diverse abilities

- Use of adapted basketball equipment and structured drills

- Deployment of sign language interpreters to enable full participation of learners who are deaf

- Use of tactile, audio, and visual cues for children with visual impairments

- Inclusive warm-up exercises and drills designed for wheelchair users

- Integration of disability awareness messaging for peers, teachers, and community members

The component is grounded in a baseline mapping of 32 schools across Nairobi, Kiambu, Kajiado, and Machakos counties. The mapping identified infrastructural, attitudinal, and systemic barriers in each school, enabling KRCS and partners to tailor interventions to the needs of each disability cluster. The BE-DI program also emphasizes capacity strengthening. Coaches, aides, and sign language interpreters participate in structured monthly and quarterly review sessions to share insights, troubleshoot challenges, and improve program delivery. Teachers receive support to integrate inclusive sports practices into their routine Physical Education classes, ensuring sustainability beyond the project period. The component concludes with county-level mini tournaments and a final End Game Tournament in Nairobi, showcasing achievements, celebrating diversity, and amplifying messages on inclusion.

## IMPLEMENTATION DATES

The Basketball Experience program in Kenya is being implemented over a multi-year period to allow adequate time for planning, capacity building, school engagement, program delivery, and measurement of behavioral outcomes.

- BE Kenya (Main Component): Implementation began in 2024 with strategic planning, mapping of schools, recruitment of coaches, development of life skills modules, and program launch. Full operational delivery is expected through 2026.

- BE-DI (Disability Inclusion Component): The Disability Inclusion phase runs from November 2025 to December 2026. This timeline reflects the need for detailed preparatory work, including school mapping, capacity-building of coaches and interpreters, contextualization of life skills manuals, and sustained delivery of inclusive basketball sessions.

Together, these timelines position the program for a comprehensive evaluation at the end of 2026, when all interventions will have been fully implemented and preliminary outcomes observed.

## LOCATIONS OF INTERVENTION

The BE and BE-DI programs are implemented across four counties:

### Nairobi County

As Kenya’s capital and most populous county, Nairobi has the highest concentration of special needs units and diverse urban communities. Despite its resources, inequality remains prevalent, especially in informal settlements. The program leverages schools with established special needs units and high student populations.

### Kiambu County

Bordering Nairobi, Kiambu hosts several special schools and inclusive education centers, making it ideal for testing blended models of mainstreaming and integration. The county also has strong sporting culture and institutional capacity, offering opportunities for scaling successful approaches.

### Kajiado County

With large rural and semi-arid regions, Kajiado faces infrastructural gaps, long travel distances, and cultural practices that may limit participation of girls and children with disabilities. Introducing inclusive sports interventions in this context addresses structural inequities and supports vulnerable learners.

### Machakos County

Machakos has underserved rural communities and schools with limited inclusive education resources. Many learners with disabilities in the county face challenges in accessing suitable sports equipment, trained staff, or adapted learning materials. The county therefore stands to benefit significantly from BE-DI interventions.

## OPERATIONAL PARTNERS IN KENYA

| Partner | Role | Contribution |
| --- | --- | --- |
| Kenya Red Cross Society (KRCS) | NGO - Lead Implementer | Program coordination, school engagement, MEAL, training, safeguarding |
| Agence Française de Développement (AFD) | Donor / Fund Manager | Financial support, oversight, reporting |
| Expertise France (EF) | Technical Support Agency | Quality assurance, coordination, administrative support |
| NBA Africa | Technical Basketball Partner | Coach training, basketball methodology, events |
| Ministry of Education (MoE) | Government Authority | School access, teacher support, policy enforcement |
| Kenya Academy of Sports (KAS) | Technical Training Partner | Coach mentoring, certification |
| Admedia | Communication agency - Communications Partner | Branding, visibility, documentation |
| County Education Offices | Local Government Partners | Approvals, field coordination |
| Disability Organizations (KISE, DPOs) | Inclusion Specialists | Technical advice, manual adaptation |

## COORDINATION SYSTEM

| Level | Actors | Frequency | Function |
| --- | --- | --- | --- |
| National Steering Committee | AFD, EF, KRCS HQ, NBA Africa, MoE, KAS | Quarterly | Strategic oversight and policy alignment |
| Project Coordination Team | KRCS Program Team, EF, Admedia | Bi-Monthly | Operational decision-making and progress review |
| County-Level Coordination | County Education Officers, KRCS County Teams, Coaches | Monthly / Quarterly | Local implementation support and troubleshooting |
| MEAL Coordination | KRCS MEAL Officers, Partners | Quarterly | Monitoring, reporting, and evidence generation |
| Coach Coordination | Coaches, Sign Language Interpreters, KRCS Field Teams | Monthly | Technical alignment and peer learning |
| Stakeholder Engagement | Parents, Teachers, DPOs, Community Leaders | Quarterly / Semi-annually | Awareness raising, accountability, inclusion promotion |

## TARGET GROUPS

### Primary Target Groups

- Learners aged 8–17: Core beneficiaries gaining life skills, confidence, and positive social behaviors through basketball.

- Learners with visual, hearing, and physical impairments: Children receiving adapted, inclusive sports opportunities that enhance participation and belonging.

- Girls with disabilities: A priority group supported through safe, empowering, and gender-responsive inclusive sports activities.

- Special needs educators, sports teachers, and PE instructors: Key implementers equipped with skills to deliver inclusive and adaptive sports sessions.

- Coaches, aides, and sign language interpreters: Support personnel ensuring accessible communication, safe participation, and inclusive coaching.

### Secondary Target Groups

- Parents and caregivers: Influencers whose engagement enhances acceptance, support, and continuity of inclusive sports participation.

- School leaders and Boards of Management: Decision-makers facilitating resource allocation, inclusive policies, and school-level integration of the programme.

- County Education and Sports Departments: Government partners aligning programme activities with county structures, priorities, and support systems.

- Disability rights organizations: Technical partners contributing to advocacy, expertise, and strengthening of disability-inclusive practices.

- Community leaders: Influential stakeholders promoting acceptance, visibility, and community support for inclusive sports.

# PROJECT COMPONENTS (KENYA – BE AND BE-DI)

# Component 1: Development of Local Sports Infrastructure

### Component 1.1 Construction and Rehabilitation of Basketball Courts

In Kenya, the project supports the construction or rehabilitation of up to two fully accessible, disability-inclusive basketball courts. In line with the global BE model, NBA Africa manages every stage of the infrastructure process financing, technical and environmental assessments, contractor selection, works supervision, and certification.

County governments play a key enabling role by providing appropriate land near inclusive schools, ensuring security, and guaranteeing long-term ownership and accessibility.

All courts are designed to BE-DI standards and include:

- Wheelchair-accessible ramps and wide pathways

- High-contrast markings to support learners with low vision

- Acoustic cues for Deaf and hard-of-hearing learners

- Gender-sensitive and accessible toilets and changing rooms

- Inclusive seating, rest zones, and viewing areas

Most construction materials are sourced locally, while high-durability tiles are imported from South Africa to ensure longevity and safe play surfaces.

### Component 1.2 Court Management, Maintenance, and Animation

To ensure sustainability, county governments commit to annual maintenance budgets covering cleaning, repairs, landscaping, and accessibility upkeep. Daily management may be delegated to local CSOs, inclusive sports associations, community sports groups, or Kenya Basketball Federation branches.

Municipalities ensure that dedicated time slots remain reserved for BE and BE-DI activities alongside broader community use.

### Achievements of Component 1 (Kenya)

- Two courts rehabilitated to universal accessibility and safety standards.

- Ongoing consultations with county education and sports departments to establish long-term court management and community-use frameworks.

# Component 2: Implementation of Socio-Educational and Inclusive Sports Programs

## Component 2.1 Development of Socio-Educational Content & Capacity Building

### A. Co-Construction of Inclusive Educational Content

NBA Africa, AFD, and a Kenyan CSO co-develop a curriculum that integrates basketball with life skills and inclusion messaging, in line with the Ministry of Education’s CBC framework. The curriculum addresses themes critical to Kenyan learners, including gender equality, health and hygiene, school transition, disability inclusion, civic engagement, environmental responsibility, youth employability, and psychosocial wellbeing.

### B. Training of Coaches, Teachers, and Inclusive Sports Personnel

Twenty coaches, balanced by gender are recruited and trained through a cascade model. Training focuses on:

- Safeguarding and child protection

- Disability etiquette and inclusive communication

- Basic Kenyan Sign Language

- Adapted basketball drills for diverse abilities

- Mobility support and safe handling

- Leadership and positive coaching behaviors

NBA experts lead annual 3-day trainings supported by continuous mentoring and refresher sessions. Coaches also train PE teachers and sports masters, ensuring programme reach across approximately 10 schools per coach.

## Component 2.2 Delivery of Inclusive Education and Awareness Activities

### I. Assemblies (Introductory Sensitization)

Short whole-school sessions introduce BE and BE-DI, promote participation, and build awareness around inclusion, gender equality, and the value of sports.

### II. Clinics (Weekly Life Skills + Basketball Sessions)

Coaches deliver weekly sessions combining structured basketball training with life skills modules. These clinics are conducted in public, inclusive, and Special Needs Unit–linked schools.

### III. Annual Basketball Experience Kenya Inclusive Tournament

A high-visibility event that brings boys, girls, and learners with disabilities together to celebrate inclusion, teamwork, gender empowerment, and community values. The tournament also showcases environmental and social themes central to the curriculum.

# Component 3: Project Management, Communication, and Capitalization

### Component 3.1 Project Management, Audits, and External Evaluations

Expertise France leads the Kenya programme’s coordination, ensuring compliance with AFD and NBA Africa standards. Responsibilities include:

- Annual planning, reporting, and financial management

- Day-to-day coordination with counties, schools, CSOs, and partners

- Oversight of independent audits and external evaluations

- Systematic data collection on beneficiaries, coaches, PE teachers, and learners with disabilities

- Quality assurance through field monitoring, digital reporting tools, and routine supervisory visits

### Component 3.2 Communication

Communication activities raise visibility for BE’s achievements and reinforce messaging on inclusion, gender equality, and life skills. This includes:

- Highlighting programme milestones and inclusive tournaments

- Producing photo/video content, success stories, and branded materials

- Coordinating with local media outlets and county communication teams

- Ensuring AFD and NBA Africa visibility across all public-facing materials

### Component 3.3 Capitalization and Legacy Development

The project documents lessons learned, innovations, and effective practices to support scale-up and sustainability beyond 2026. Capitalization focuses on:

- Demonstrating the value of combining sports with life skills education

- Documenting disability-inclusive adaptations pioneered in Kenya

- Capturing community, coach, teacher, and parent perspectives

- Producing knowledge products for local partners and future donors

These insights feed directly into discussions on the programme’s legacy, including:

- Sustainable court management models

- Integration of BE modules into county and school programmes

- Opportunities to collaborate with new donors, NGOs, private-sector partners, and government entities

- Strategies for scaling the BE model within and beyond current counties

# OBJECTIVES OF THE ASSIGNMENT

## Rationale for the final evaluation (Kenya BE and BE-DI Projects)

The Basketball Experience (BE) and Basketball Experience – Disability Inclusion (BE-DI) projects represent the first project within Expertise France’s portfolio on sport, education, and youth development in Kenya. This project is among the first large-scale country level deployments funded by AFD under its Sport and Development strategy, and it reflects a strategic commitment to using sport as a driver for education, life-skills acquisition, gender equality, and social inclusion particularly for children and young people with disabilities. As such, expectations for the Kenyan components of the programme are high at both operational and strategic levels.

Given their importance, Expertise France is commissioning a final external evaluation of the BE project in Kenya. This evaluation serves as a key accountability mechanism to AFD, Expertise France, the Kenya Red Cross Society, NBA Africa, and national stakeholders in Kenya’s Ministries of Education and Sports. It aims to assess the overall impact, relevance, coherence, effectiveness, efficiency, and sustainability of the interventions implemented since 2024.

This final evaluation will focus specifically on the Kenyan context, where the BE and BE-DI components have been fully implemented. It will document results achieved, challenges encountered, and lessons learned throughout the implementation cycle. The evaluation is also intended to support strategic learning, generating evidence and good practices that will inform future programme design, scale-up opportunities, and policy dialogue with Kenyan education and sports authorities. The findings will be shared with national stakeholders and programme partners to strengthen future interventions aimed at promoting inclusive access to sports, life-skills development, and positive youth outcomes across Kenya.

## MAIN OBJECTIVE

The final evaluation seeks to provide a comprehensive, independent, and evidence-based assessment of the Basketball Experience (BE) and Basketball Experience – Disability Inclusion (BE-DI) programs implemented in Kenya. The evaluation will examine the relevance, coherence, effectiveness, efficiency, impact, and sustainability of the programs, while drawing direct analytical alignment with the approach used during the Mid-Term Evaluation to ensure methodological consistency and balanced coverage of all components. More specifically, the evaluation aims to:

- Assess overall project performance, examining the relevance, coherence, efficiency, and effectiveness of the project’s design, management, and implementation arrangements. The evaluation will analyze internal and external factors that have influenced performance, including recurring operational constraints, contextual challenges within schools and communities, and institutional or coordination-related barriers.

- Review the implementation strategy and governance arrangements, including strategic and operational choices made during implementation. The evaluation will confirm or challenge these choices and propose context-appropriate, actionable recommendations to strengthen coordination, management, and delivery mechanisms.

- Generate learning and inform future programming, by identifying good practices, innovations, and lessons learned from project implementation across different school and community settings in Kenya. The evaluation will formulate practical recommendations to consolidate results achieved, address outstanding gaps, and enhance the effectiveness, equity, and sustainability of similar interventions beyond the project period.

The evaluator will be required to present clear, evidence-based analyses, demonstrating cause-and-effect relationships and identifying factors that have enabled, hindered, or impeded progress. The evaluation findings and recommendations should support accountability to stakeholders, facilitate strategic and operational decision-making, and promote organizational learning for implementing partners and relevant institutions.

## SCOPE OF WORK

The evaluation will cover all aspects of BE and BE-DI program implementation

- Period Covered by the Evaluation: The evaluation will cover the period from July 2024 to December 2026, assessing the full implementation of the BE and BE-DI programs.

- Geographical Coverage: The evaluation will focus on the four target counties: Nairobi, Kiambu, Kajiado, and Machakos, where the programs have been implemented.

- Components: All aspects of the BE and BE-DI programs will be examined, including program design, training and mentorship, life skills sessions, inclusive basketball clinics, physical infrastructure, operational coordination, and overall program outcomes.

- Beneficiaries: The evaluation will consider the perspectives and involvement of institutional partners and other stakeholders, including KRCS, NBA Africa, EF, AFD, Ministry of Education, KAS, Admedia, County Education Offices, disability organizations, PE teachers, inclusive coaches, aides, learners with and without disabilities, girls, and local communities

# CRITERIA AND EVALUATIVE QUESTIONS

The final evaluation of the Basketball Experience (BE) and Basketball Experience –Disability Inclusion (BE-DI) projects in Kenya will apply five evaluation criteria based on the OECD Development Assistance Committee (DAC) framework: relevance, coherence, effectiveness, efficiency, and impact, with an additional focus on sustainability/viability.

The evaluative questions below were developed in alignment with the Kenyan implementation context and in consultation with the program’s steering group. They will be reviewed, refined, and specified by the evaluator at the start of the evaluation phase and validated in the scoping/inception report.

## EVALUATION CRITERIA AND SPECIFIC EVALUATIVE QUESTIONS (KENYA BE AND BE-DI FINAL EVALUATION)

| Evaluation Criteria | Specific Evaluative Questions |
| --- | --- |
| Coherence | 1.1. To what extent have synergies between BE/BE-DI and other related initiatives implemented by Expertise France, AFD, NBA Africa, KRCS, Ministry of Education, and Ministry of Sports been effective in strengthening the socio-educational integration of young people? 1.2. To what extent are BE/BE-DI intervention models (school-based, disability-inclusive, life-skills oriented) complementary to existing county and national systems supporting access to sports and inclusion of youth, particularly in basic education institutions and special-needs schools? 1.3. To what extent have BE and BE-DI effectively collaborated with initiatives implemented by Expertise France, AFD, NBA Africa, KRCS, the Ministry of Education, and the Ministry of Sports to enhance the socio-educational integration of young people? 1.4. How have these partnerships strengthened the projects’ outcomes, leveraged resources, and fostered knowledge sharing? |
| Effectiveness | 2.1. To what extent has the school-based intervention strategy enabled the acquisition of life skills and encouraged consistent sports practice among children participating in BE and BE-DI activities? 2.2. To what extent did the training and continuous support provided to teachers and coaches improve the quality and the accessibility of the basketball and life skills development sessions delivered to children, including learners with disabilities? 2.3. To what extent have the programs particularly training supported by NBA Africa contributed to the professional development, recognition, and potential employability of coaches and teachers (including women and disability-inclusive coaches) within Kenya’s sports ecosystem? 2.4. What perceived or documented changes in students’ life skills (communication, leadership, confidence, etc.) can be attributed to the BE and BE-DI project? 2.5. To what extent have children participating in BE and BE-DI activities developed increased interest, motivation, and commitment toward regular sports practice, both inside and outside school settings? 2.6. To what extent did the project strengthen the commitment, capacity, and coordination of schools, clubs, teachers, coaches, and other structures to implement regular and inclusive activities 2.7 To what extent did students (including girls, students with disabilities, and vulnerable students) effectively participate in the proposed activities on a regular, active, and ongoing basis 2.8 To what extent have inclusion issues been effectively integrated into project deployment in Kenya including gender equality, meaningful participation of learners with disabilities (visual, hearing, and physical/mobility), and engagement of vulnerable or marginalized learners? To what extent were communities living near rehabilitated grounds, but not directly participating in the program, considered and included? 2.9. What unexpected results positive or negative have emerged from the BE and BE-DI projects, and how have these outcomes affected beneficiaries, schools, communities, and overall project implementation? What lessons can be drawn from these experiences to inform the design and delivery of future interventions? 2.10. How have the effects of BE and BE-DI varied across counties, schools, and different types of beneficiaries (e.g., learners with and without disabilities, girls, teachers, communities), and what factors explain these differences? How can future interventions be adapted to address these variations and maximize effectiveness, inclusion, and equitable impact? |
| Efficiency | 3.1. To what extent were human, financial, and material resources adequate and efficiently allocated to meet project needs in Kenya, ensuring optimal cost-effectiveness (including school selection, coaching resources, and accessibility adaptations for disability inclusion)? 3.2. To what extent did the available resources (including rehabilitated courts, equipment, trained coaches, and support from KRCS branches) enable the project to meet planned deadlines and implementation targets? To what extent were the conditions favorable to achieving the expected outputs/targets (quality and quantity) within the established timeframe? |
| ## Relevance | 3.1. How well did the design of the Basketball Experience and Basketball Experience Disability Inclusion projects reflect the real needs, priorities, and everyday challenges faced by Kenyan learners, schools, and communities, particularly in supporting youth development, inclusive education, and access to safe spaces for sport? 3.2. How closely were the project’s objectives, target groups, and ways of working aligned with national and county priorities in education, sports development, child protection, gender equality, and disability inclusion, both at the start of the project and by its completion? 3.3. How relevant and context-appropriate were the chosen delivery approaches, such as the school-based model, integration into the school calendar, and use of rehabilitated courts, in addressing the specific participation barriers faced by girls, learners with disabilities, and other vulnerable children? 3.4. To what extent did the project’s focus on life skills, citizenship, well-being, and inclusion continue to respond to the changing needs and expectations of learners, schools, and communities over the course of implementation? 3.5. How well do the Basketball Experience and Basketball Experience Disability Inclusion models remain relevant and feasible for future integration or scale-up in national systems, given the current institutional and policy context? |
| Sustainability / Viability | 4.1. To what extent are the results already achieved or currently being achieved likely to be maintained or expanded over time within participating schools and communities? What conditions (policy support, school ownership, teacher capacity, availability of equipment, community engagement, disability-inclusion structures) are necessary to ensure long-term sustainability and strengthening of outcomes? |
| Impact | 5.1 To what extent has participation in BE and BE-DI contributed to lasting engagement in sports and personal development among young people, including confidence, teamwork, and social inclusion? 5.2 What measurable behavioral, social, or attitudinal changes have resulted from the projects, particularly in relation to inclusion of learners with disabilities, gender equity, and respect for diversity? 5.3 How has the project influenced school dynamics and community engagement, including the perception of sports as an educational and developmental tool? 5.4 How have the effects of BE and BE-DI varied across regions, schools, and different beneficiary groups, what unexpected outcomes have emerged, and to what extent are these changes likely to be sustained beyond the project period? |

The consultants must review, refine, and specify each of the evaluation questions above to ensure they sufficiently cover all key stages of the BE and BE-DI project cycle in Kenya.

The consultants must additionally examine how well the cross-cutting themes of gender equality, disability inclusion, and social cohesion were considered during the design, formulation, implementation, and monitoring of the projects and assess the extent to which these themes are reflected in results, practices, and participation patterns.

# DESCRIPTION OF THE MISSION (KENYA FINAL EVALUATION ADAPTATION)

## METHODOLOGY ADOPTED

The consultants must take into account the different legitimate points of view expressed by all stakeholders and conduct the evaluation impartially. This consideration must be reflected through systematic involvement of the various BE and BE-DI stakeholders throughout the evaluation process.

## PROCESS

Consultants are requested to closely associate Expertise France (EF) in the construction of their evaluation reasoning, from the scoping note to the final report presentation. Preliminary findings and analysis must be shared at the end of field missions via an interim PowerPoint report. Frequent meetings with Expertise France team in Kenya and in Paris will be organized to set the right path of the evaluation.

## START-UP PHASE

Consultants must:

- Gather and consult all relevant BE and BE-DI documentation;

- Identify all program stakeholders;

- Reconstruct intervention logic using the logical framework and theory of change in order to: (i) clarify the objectives of the intervention and translate them into a hierarchy of expected changes, (ii) help assess the internal consistency of the intervention, and (iii) identify the initial assumptions (or postulates, often implicit) that guided the design of the project a priori, and evaluate their validity afterwards

- Refine the evaluation framework specifying evaluation questions, judgment criteria, and indicators. More specifically, this will involve: (i) identifying the main questions that will be used to focus the evaluation work on a limited number of key points; (ii) establishing the steps in the reasoning process that will enable the questions to be answered (judgement criteria); (iii) specifying the indicators to be used to answer the questions and the corresponding sources of information (documentation, interviews, focus groups, surveys, etc.).

- Based on this methodological work, the consultant will prepare a scoping note (see template in the appendix). This scoping note will be reviewed and discussed in a meeting with the steering group, providing an opportunity to clarify how the consultants intend to structure the evaluation process and to assess its feasibility. If the intervention logic is reconstructed, it will be important to ensure that any objectives redefined by the evaluator are validated and shared with the project team and the project manager. This preparatory phase is crucial, as it allows the proposed methodology to be confirmed and agreed upon. A list of documents available for consultation is provided in the appendix to these Terms of Reference.

Deliverable: Scoping Note

## DATA COLLECTION PHASE

Document Review: Systematic review of program documents to inform evaluation questions and identify gaps. The review of relevant documents should be conducted in a systematic way, following the methodology agreed upon during the start-up phase. Activities carried out during this phase should provide preliminary insights for each evaluation question, clearly communicating the information already gathered and any limitations identified. They should also help to highlight remaining gaps, missing information, and initial hypotheses that will need to be explored further during the evaluation.

Primary Data Collection: Conducted in Nairobi, Kiambu, Kajiado, Machakos targeting learners, teachers, coaches, parents, and community stakeholders. Methods include interviews, focus groups, surveys, and observation. Data collection will employ both qualitative and quantitative methods, as proposed by the consultants and based on the sample defined by the evaluator. These methods will have been outlined in the scoping note and validated by project stakeholders prior to implementation.

Following the data collection phase, the evaluator will conduct a feedback and review meeting with partners in the field, the project team, and AFD to discuss preliminary findings.

At the conclusion of the data collection phase, the consultants will produce an interim report, which may take the form of a PowerPoint presentation. This report will allow the initial data collected to be shared, ensuring the traceability of findings and conclusions back to the underlying data.

The interim report will form the basis for a meeting between the evaluation team and the evaluation steering group, whose main objectives are to:

- Establish a common understanding of the data collected;

- Outline the main points of cross-analysis;

- Identify any gaps in the data that require additional collection, potentially through remote means.

All presentation materials used to communicate preliminary results at the end of the field mission will be shared with the project team. These documents should ensure that the evaluation findings and conclusions are fully traceable to the data collected.

Deliverable: Interim report and presentation support (PowerPoint)

## REPORTING PHASE

- Provisional Evaluation Report: A provisional report, not exceeding 40 pages excluding appendices (see proposed outline in Appendix 4), will be produced by the consultant(s) following additional analysis and quality control, accompanied by a PowerPoint presentation. This provisional report will serve as the basis for a feedback meeting involving the evaluation team, the evaluation steering group, and AFD. The primary objectives of this meeting are to:

- Present and discuss the preliminary conclusions for each evaluation question;

- Ensure that these conclusions are adequately substantiated and identify any gaps that require further analysis;

- Refine the wording of conclusions to establish a consensus on the final findings;

- Collaboratively develop the recommendations arising from the evaluation.

In addition, the consultants will be required to provide specific conclusions and recommendations regarding the integration of gender equality considerations within the project.

- Final Evaluation Report:. The consultants will then produce a final report, which will incorporate the feedback and observations of Expertise France and AFD, as well as the recommendations identified during the evaluation. A two-page summary of the report will also be provided in cases where feedback or observations include differences of opinion not shared by the consultants, these may be appended to the final report, along with comments from the consultants to provide context.

Deliverables:

- Final evaluation report (Word/PDF)

- Summary sheet (2 pages, infographic mandatory)

- PowerPoint presentation of restitution workshop

## EXPECTED DELIVERABLES AND TIMELINE

| Phase | Deliverables | Max Pages | Person-Days | Delivery Date |
| --- | --- | --- | --- | --- |
| Start-up Phase | Kick-off meeting | - | 1 | TBD |
|  | Scoping note (evaluation matrix) | 15 | 5 | TBD |
| Data Collection Phase | Field mission report (executive summary / hot notes) | 10 | 5 | +7 days after field mission |
|  | Interim report and presentation support | 30 | 16 | TBD |
| Reporting Phase | Provisional evaluation report | 40 | 10 | TBD |
|  | Final evaluation report | 45 | 5 | TBD |
|  | Summary sheet | 2 | 1 | TBD |
|  | Restitution workshop presentation | 30 slides max | 2 | TBD |

PowerPoint presentation must be prepared for each steering meeting.

# ORGANIZATION OF WORK (KENYA FINAL EVALUATION ADAPTATION)

### Management and Governance

Evaluation managed by EF with support from a Steering Group: EF Project Manager in Paris, EF Local coordinator for BE program based in Nairobi, EF MEAL Coordinator/officer based in Paris, KRCS Program Lead. Other stakeholders may join depending on needs.

Roles:

- Advise on evaluation design;

- Approve methodological adjustments;

- Validate deliverables.

Meetings:

- Start-up: Validate the general implementation methodology, the data collection plan, and the expected presentation of deliverables, and validate scoping note;

- Mid-term: respond to the initial analyses and findings, once the data collection phase is complete (validation of the interim report);

- Finalization: Co-construct conclusions and recommendations.

- To validate the final report based on the scope of the points remaining to be decided, otherwise by email.

## COORDINATION ARRANGEMENTS

Consultants are expected to actively engage Expertise France throughout the evaluation process, maintaining regular communication from the development of the scoping note through to the presentation of the interim report. In particular, findings and preliminary analyses must be shared at the end of the field mission, prior to drafting the interim report.

The services will be delivered both remotely and on-site in Kenya. The kick-off meeting, scoping interviews, and final presentation may be conducted via videoconference, depending on the consultants’ arrangements. Whenever feasible, these scoping and presentation meetings should be conducted in person.

## ORGANIZATION OF FIELD MISSIONS

The evaluators will organize their missions on the field and provide their own logistics support. Expertise France and AFD can provide invitation letters for visa or mission orders if needed. Final deliverables to be in English.

## Indicative Timetables

- Duration: 11 weeks

- Workload: 45 man-days

- Timeframe: June to August 2026.

- The selected evaluation team must include in its bid a detailed work plan specifying the days worked per activity and per member of the evaluation team, as well as indicative dates and locations. This work plan will be discussed and approved at the kick-off meeting. A clear timetable will set out the milestones with the provisional dates of any missions.

## REQUIRED QUALIFICATIONS AND PROFESSIONAL PROFILES

The evaluation team should include professionals with demonstrated expertise in international cooperation and program evaluation, and sports for development and/or inclusive education and/or and final program evaluation.

### Lead Evaluators

The mission will ideally be led by a pair of experts with complementary profiles in public policy evaluation and on the theme of sport, education, and social inclusion.

### Expert, Head of Mission

The Head of Mission will have to:

- Hold a minimum university-level Master’s degree (BAC+5) in a field relevant to the mission: public administration, social sciences, educational sciences, international cooperation, evaluation, or equivalent.

- Have at least 10 years of professional experience in development monitoring and evaluation and/or in the education, sports, and/or sport for development sectors.

- Have completed at least 3 international cooperation project evaluation missions, as head of mission, including at least one mission in education, sport, and/or sport for development.

- Have experience in multi-stakeholder coordination.

- Experience in similar projects and knowledge of project management would be highly appreciated.

- Excellent command of office tools (MS Office: Word, Excel, PowerPoint or their equivalent LibreOffice) and the Internet.

- Excellent communication and organizational skills.

- Excellent command English, written and spoken (good writing, synthesis, and analysis skills). French would be appreciated.

- Expert
This second expert will:

- Hold a minimum university-level Master’s degree (BAC+5) in a field relevant to the mission: public administration, social sciences, educational sciences, international cooperation, evaluation, or equivalent.

- Have at least 5 years of professional experience in the education, vocational training, and/or sports sector.

- Experience in similar projects and knowledge of project management would be highly appreciated.

- Having carried out at least 1 international cooperation project evaluation mission would be an asset.

- Experience of multi-stakeholder coordination.

- Excellent command of office tools (MS Office: Word, Excel, PowerPoint or their equivalent LibreOffice) and the Internet.

- Excellent communication and organizational skills.

- Excellent command English, written and spoken (good writing, synthesis, and analysis skills). French would be appreciated.

### Additional Requirements

- Ability to travel to the project counties (Nairobi, Kiambu, Kajiado, Machakos) for fieldwork.

- Demonstrated commitment to inclusivity, impartiality, confidentiality, and adherence to ethical standards.

- Ability to meet tight deadlines and produce deliverables according to the timeline required by EF and KRCS.

- Independence from the project implementers to ensure neutrality and objectivity

- Expected Team Organization: The evaluation team should consist of two independent experts, designated by the lead international expert. The proposal must clearly outline the allocation of roles and responsibilities among team members throughout the evaluation process. This proposed division of tasks will be reviewed, discussed, and validated during the scoping meeting.

## PROPOSAL SUBMISSION REQUIREMENTS

Applicants should submit:

- Technical proposal Demonstrating an understanding of the terms of reference, proposed methodology, composition of the evaluation team (with CVs and descriptions of similar experiences), detailed work plan and distribution of roles and responsibilities within the evaluation team; activity schedule.

- Financial proposal detailing the Overall budget for the evaluation, including the following budget items: daily cost of each contributor; breakdown of time spent per contributor and per stage of work; ancillary costs (additional services and documents); mission expenses (in the event of missions to Kenya): airfare, per diem (including hotel, meal and local transport costs) and visa fees.

## EVALUATION AND SELECTION CRITERIA

The selection process will be based on a combined assessment of both the technical and financial proposals. The maximum overall score is 100 points, distributed as follows:

## 1. Technical Offer

Maximum score: 80 points

The technical proposal will be evaluated on the basis of four key criteria designed to assess the bidder’s understanding, methodological rigor, operational planning, and team capacity. The breakdown is as follows:

### Criterion 1: Understanding of the Terms of Reference and Objectives

Maximum: 5 points

This criterion assesses the bidder’s comprehension of:

- the scope and purpose of the assignment,

- the strategic and operational objectives,

- the expected deliverables and final use of the evaluation results.

A strong proposal should clearly demonstrate a nuanced and realistic understanding of the context, main issues, and anticipated challenges.

### Criterion 2: Methodological Approach and Quality Assurance

Maximum: 35 points

This criterion evaluates the robustness, relevance, and feasibility of the proposed approach, including:

- the overall methodology and analytical framework,

- the coherence and suitability of the proposed tools,

- the mechanisms for quality control and consistency of outputs,

- the identification and mitigation of potential risks, limitations, and operational challenges.

A solid proposal should present a clear, credible, and context-appropriate methodological strategy that ensures reliability and rigor throughout the assignment.

### Criterion 3: Organization of Tasks and Timeline

Maximum: 10 points

This criterion examines the effectiveness of the proposed work plan, including:

- task distribution and sequencing,

- alignment of activities with the proposed timeline,

- the feasibility and realism of the schedule,

- the organization of internal coordination and reporting mechanisms.

A well-structured proposal will demonstrate the team’s ability to efficiently manage time and resources to deliver high-quality outputs within the expected timeframe.

### Criterion 4: Experience and Qualifications of the Evaluation Team

Maximum: 30 points
This criterion assesses the expertise, complementarity, and professional experience of the proposed team, including:

- demonstrated experience in similar evaluations or thematic areas,

- qualifications relevant to the assignment,

- familiarity with the geographical and sectoral context,

- balance and complementarity of profiles within the team.

Proposals are expected to clearly highlight the added value brought by each team member and how their combined expertise strengthens the execution of the assignment.

## 2. Financial Offer

Maximum score: 20 points

The financial proposal will be evaluated using the following standard formula:

Financial score = (Maximum points × Lowest financial bid) / Financial bid of the candidate being evaluated

The financial offer is only considered if the technical proposal reaches the minimum required quality threshold. Unrealistically low or inconsistent budgets may be subject to clarification.

Interview Phase (If Applicable)

Following the assessment of the technical bids, Expertise France may invite shortlisted candidates to participate in an interview.
This interview aims to:

- clarify the methodological approach,

- assess the team’s operational understanding,

- confirm the coherence and feasibility of the proposed work plan.