Expert in Environmental/Climate Economics and Green Budgeting

# Technical support to implement green budgeting practices in Czech Republic

# Duty station: remote

**Contract type:** service contract

**Duration:** 30 months

**Total number of working days:** 210

**Financing Authority:** Task Force for Reform and Investment (SG REFORM) of the European Commission.

**Implementing Partner:** Expertise France

**Deadline for application is:** 30 August 2025

**General context**

Expertise France is a public agency that designs and implements international technical cooperation projects and is a member of the French Development Agency Group. The Agency operates in four priority areas:

* democratic, economic and financial governance
* peace, stability and security
* climate, agriculture and sustainable development
* health and human development.

In these areas, Expertise France engineers and implements capacity-building projects, mobilises technical expertise and acts as a project coordinator, bringing together public expertise and private know-how.

With a turnover of 450 million euros in 2024 and more than 350 projects underway in 140 countries, Expertise France is the benchmark public agency for French international technical cooperation.

The portfolio of intra-European projects is growing, in particular projects financed by the European Commission's SG REFORM (European Commission's Reform and Investment Task Force).

**Mission Description**

# In the framework of the project Implementing Effective Green Budgeting practices, Expertise France is recruiting an expert in Environmental and Climate Economics, Green Budget Tagging, with strong knowledge of Czech´s Republic Public Financial Management (PFM) context and experience/knowledge of latest policy developments at EU level, namely Do No Significant Harm, green budgeting developments at EU level.

The expert will provide technical support to officials at the Czech Ministry of Finance by: **refining and testing the methodology for assessing and reporting climate-relevant expenditures, providing tailored recommendations for effective governance and coordination of green budgeting practices, and designing and implementing training on methods to conduct evaluations of environmental and decarbonisation spending.**

The expert will collaborate with officials from the Green Budgeting Unit at the Czech Ministry and focal points from relevant line ministries, along with Expertise France´s Project Management team, policy officers from the Task Force for Reform and Investment (SG REFORM), and technical experts from the European Commission Joint Research Centre (JRC).

Project and Country-specific context:

Green Budgeting aims to align national budgets with sustainability objectives by systematically identifying, assessing, and reporting expenditures and revenues that impact climate and environmental goals. This reform initiative enhances transparency, policy coherence, and informed decision-making, supporting the transition to a sustainable and resilient economy.

The reformed **EU Economic Governance Framework**, which entered into force in April 2024, aims to ensure sound and sustainable public finances while promoting inclusive and sustainable economic growth. The reform introduces medium-term fiscal structural plans, requiring Member States to outline fiscal, structural, and investment policies over a 4–5-year horizon, with a macroeconomic outlook spanning up to seven years for reforms and investments. This framework aligns public finances with country-specific challenges and EU priorities, including the European Green Deal.

The recently adopted **EU Directive 2024/1265[[1]](#footnote-1)** and the new **EU Economic Governance Framework** emphasize the importance of aligning fiscal policies with sustainability and climate objectives. The Directive requires Member States to report on macro-fiscal risks arising from climate change, climate-related contingent liabilities, and fiscal costs of disasters.

The **Green Deal Communication**, the **Fit for 55 package[[2]](#footnote-2)**, and the **reformed EU Economic Governance Framework** set an ambitious policy context for addressing climate change, emphasizing the need to align public finances with climate and environmental objectives. Green Budgeting is critical to achieving these goals.

Between 2021 and 2024, the Commission implemented the **Green Budgeting Training Programme[[3]](#footnote-3)**, a multi-country technical support project under the Technical Support Instrument (TSI). This program, based on the European Union Green Budgeting Reference Framework, provided capacity-building in Green Budgeting to 23 Member States. It consisted of four modules covering foundational principles, tagging methodologies, environmental impact assessments, and peer-to-peer exchanges. The program:

* Trained approximately 1,200 participants.
* Enabled Member States to develop and implement Green Budgeting frameworks at the national level.
* Fostered cross-border collaboration and established a community of Green Budgeting Practitioners among public officials across the EU.

**Implementing Effective Green Budgeting practices**

These technical support needs shall be addressed in the framework of this new project for Implementing Effective Green Budgeting practices. The Beneficiary Authorities are facing unique challenges in implementing green budgeting practices. Each country has its own specific challenges, such as developing tagging methodologies, institutionalizing green budgeting, and integrating environmental impact assessments into budgeting processes. Despite progress made, each country require technical support to address gaps in capacity, governance, and data management, and to refine methodologies for identifying and categorizing green expenditures. The countries will benefit from the action through tailored support as well as common activities to share experiences, develop and strengthen methodologies, and foster cross-border collaboration.

Croatia, Czech Republic, Cyprus, Denmark, France, Ireland, Portugal, Slovakia, Slovenia and Spain have requested support from the European Commission under Regulation (EU) 2021/240 establishing a Technical Support Instrument ("TSI Regulation"). The request for technical support was assessed by the European Commission in accordance with the criteria and principles referred to in Article 9 of the TSI Regulation and was selected for funding.

The national authorities that requested technical support and will benefit from this Project are:

* Ministry of Finance of the Republic of Croatia (Ministarstvo financija)
* Ministry of Finance of Cyprus
* Ministry of Finance of the Czech Republic (Ministerstvo financí České republiky)
* Ministry of Finance of Denmark (Finansministeriet)
* General Direction for Public Finances and Budget Directorate, Ministry of Economics, Finance and Industrial and Digital Sovereignty (Direction Générale des Finances Publiques (DGFiP) and Direction du Budget (Ministère de l’Économie, des Finances et de l’Industrie)
* Department of Public Expenditure and Reform, Department of Finance of Ireland (An Roinn Caiteachais Phoiblí, Bonneagair, Seirbhísí Poiblí, Athchóirithe agus Digiteachaithe)
* Office for Economic Policy and International Affairs, Ministry of Finance (Gabinete de Planeamento, Estratégia, Avaliação e Relações Internacionais (GPEARI) – Ministério das Finanças)
* Ministry of Environment of Slovakia (Ministerstvo životného prostredia Slovenskej republiky)
* Ministry of Finance of Slovenia (Ministrstvo za finance)
* Ministry of Ecological Transition and the Demographic Challenge of Spain (Ministerio para la Transición Ecológica y el Reto Demográfico)

This project has two strands of technical support:

1. Five Standalone Requests: These focus on tailored technical support for implementing Green Budgeting practices at the national level in Cyprus, Czechia, Denmark, France (sub-national), and Portugal. The support includes developing methodologies for tagging climate-relevant expenditures, enhancing governance frameworks, and building capacity within national ministries.
2. Civil Servants Exchange: This component facilitates knowledge-sharing and capacity-building among Member States. It includes participation from the five standalone project beneficiaries (Cyprus, Czechia, Denmark, France, and Portugal) as well as Croatia, Ireland, Slovakia, Slovenia, and Spain. The exchange is open to other Member States on demand, fostering a collaborative approach to Green Budgeting reforms and the dissemination of best practices across the EU.

**Czech Republic**

Given that financing decarbonisation is expected to be capital-intensive, the Czech Ministry of Finance seeks support in developing tools for effective resource management and efficiency evaluation. A new green budgeting unit has been established as of January 2025 to advance green budgeting practices. The Unit has recently developed a draft green budget tagging methodology to be refined and tested before the end of 2025.

Civil Servants from the Czech Ministry of Finance and Ministry of Environment acquired theoretical and practical knowledge on tagging expenditures and revenues and learnt from the methodological approaches used by peers in Austria and France, through the Green Budgeting Training Programme. In this new Technical Support Instrument for implementing effective green budgeting practices, the Czech Ministry of Finance has requested support to continue the improvement of capacity and strengthen efforts to address gaps for developing green budgeting practices. The Ministry of Finance seeks technical support in designing and embedding Green Budgeting practices, particularly in integrating tagging methodologies into budgetary processes. Green Budgeting is also one of cross-cutting measures in the Czech National Climate Adaptation Strategy approved in 2021 and to be delivered by 2026.

# Deliverables and work plan

|  |  |
| --- | --- |
| **Outputs and estimated timeframe** | **Activities** |
| Technical Report of the Inception phase  July- September 2025 | Producing a technical country report where the country-specific analyses and points of actions are captured and specific recommendations provided. To produce this Output, the designated expert will collaborate closely with the Green Budgeting team in the Czech Ministry of Finance and relevant technical staff from other line ministries in the following activities   * Conduct consultations and desk-research to understand the budgetary process, structure and legal framework of Czechia’s national budget, as well as to get a clear overview of the draft green budget tagging methodology, relevant RRF deliverables, climate and environmental policy objectives and other EU and national legislation related to Green Budgeting, including relating to the Do No Significant Harm (DNSH) principle * Provide technical support to improve and finalise the draft tagging methodology in accordance with international best practices and with the environmental objectives of the EU Taxonomy. Particularly, the expert will review and provide recommendations on the scope (sectors/measures and budget items); coverage (environmental or climate related axes); definition of green and brown budget items; rating method; scientific sources; task-force group, and tools used for conducting the tagging (excel or other suitable and available tool). In addition, the expert shall agree with the team on the timeline and technical staff to be involved in the pilot implementation of the methodology * Identify the existing knowledge gaps in methods for evaluating environmental protection or decarbonisation expenditure, e.g., risk assessment, cost-benefit analysis and cost-effectiveness analysis, or other metrics for measuring the efficiency and effectiveness of green spending. * Participate in the kick-off event of the project |
| Technical Report of the Tagging Methodology  September- December 2025 | Produce a technical report including: the refined version of the methodology; an analysis and summary of the application of the pilot methodology focusing on strengths and areas of improvement; an operational guide on how to use the tagging methodology; recommendations on how to integrate tagging in the budget process; a roadmap to develop a permanent task-force that involves all relevant line ministries, agencies, and parliamentary representatives; a communication plan to obtain information on budget lines from line ministries; templates for improving monitoring and reporting, and an overview of the tagged green and brown budget items in an easily accessible manner that ensures transparency in presenting findings to policymakers. To produce this Output, the designated expert will collaborate closely with the Green Budgeting team in the Czech Ministry of Finance and relevant technical staff from other line ministries in the following activities:   * Conducting one or two workshops with the relevant technical staff to prepare for the tagging implementation. * Screening all budget lines in the national budget based on the agreed classification criteria. * Identifying subsidies, tax incentives, and direct expenditures that conflict with Czechia’s climate targets. * Cross-referencing results with fossil fuel subsidies identified by the Ministry of Finance, Ministry of Environment, and Ministry of Trade. * Assessing Budgetary Impact of Brown Budget Items, including estimating the fiscal weight of brown budget items in relation to the total national budget; and identifying potential areas for reallocation of funds toward green investments. * Developing a comprehensive report on brown budget allocations with accessible data visualizations to ensure transparency in presenting findings to policymakers. * Drafting the report (the expert shall ensure continuous feedback from the Green Budgeting team at the Czech Ministry of Finance) |
| Report with guidelines on other green budgeting practices  January- April 2026 | Produce a technical report with guidelines on methods for tracking and measuring the efficiency and effectiveness of green spending, e.g., risk assessment, cost-benefit analysis and cost-effectiveness analysis, or other metrics. Based on the knowledge gaps identified in the inception phase, the designated expert will develop a training curriculum with at least 4 thematic training modules. The content of the training modules shall focus on brief theoretical content and significant practical content, e.g., case studies, exercises, discussions, and other hands-on activities. To produce this Output, the designated expert shall implement the following activities:   * Draft the report with guidelines on methods for evaluating efficiency and effectiveness of green spending, with recommendations on how Czechia can improve its efforts for evaluating efficiency and effectiveness in Czechia´s fiscal context * Deliver training on the implementation of the guidelines that would entail to: * Develop the training curriculum and identify relevant training participants * Implement the training sessions at the Ministry of Finance or online * Evaluate training satisfaction |
| Contribution to peer exchanges  Through the whole project duration | Accompanying the Czech officials to workshops and discussions with peers from other EU Member States and reporting good practices that could be replicable or adaptable to the Czech context |
| Contribution to capitalisation material  Through the whole project duration | Providing input to publications or other material, e.g. information on key findings and best practices from the Tagging Methodology and Guidelines on other Green Budgeting Practices. The aim of the capitalisation material is to disseminate potential common approaches or frameworks that can guide coherent and effective green budgeting implementation across Member States. |
| Final report and final conference  September 2027-December 2027 | Reporting on the key achievements, challenges, and lessons learned from the green budgeting technical support provided. Participate in the final conference by presenting the progress on Green Budgeting practices achieved in Czech Republic |

*Note: the precise dates for the activities will be agreed between the selected Expert and the project team.*

# Desired profile

* Master’s or PhD in Environmental and/or Climate economics, Environmental fiscal policy, Green Public Financial Management, other relevant fields with at least 7 years of professional experience in the outlined areas;
* Knowledge of Czech Republic´s decarbonisation and environmental objectives, and fiscal policy;
* Track record of providing technical support to the development and implementation of Green PFM tools or climate finance, as well as experience in executing capacity building activities;
* Track record in strategic engagement with multidisciplinary teams, and with senior-level government, private sector, and/or international cooperation partners;
* Fluency in English. Fluency or good level of Czech is an asset.
* Experience with providing technical support in projects financed by the European Commission is an asset.

1. https://eur-lex.europa.eu/legal-content/EN/TXT/PDF/?uri=OJ:L\_202401265 [↑](#footnote-ref-1)
2. https://www.consilium.europa.eu/en/policies/fit-for-55/ [↑](#footnote-ref-2)
3. <https://reform-support.ec.europa.eu/what-we-do/revenue-administration-and-public-financial-management/supporting-implementation-green-budgeting-practices-eu_en> [↑](#footnote-ref-3)