TERMS OF REFERENCE
AND TECHNICAL SPECIFICATIONS

I.  General information

| Assignment name | Provision of Expert Consultation Services on Psychological Interventions, Correctional and Probation Programmes and Professional Training in Penitentiary and Probation Systems |
| --- | --- |
| Beneficiary | Ministry of Justice of Ukraine and relevant penitentiary and probation institutions |
| Name of the project and code | PravoJustice4EU, 25GEO0C350 |
| Country | UKRAINE |
| Total estimated number of days | 42 |

II. Context and justification of the need

The PravoJustice4EU Programme, implemented by Expertise France (EF) with funding from the European Union and the French Ministry for Europe and Foreign Affairs, supports Ukrainian authorities in the continued reform and strengthening of the justice sector.

PravoJustice4EU is structured around two specific objectives: supporting the EU accession process by aligning the Ukrainian justice system with EU standards, including independence, efficiency, quality, integrity, transparency and access to justice; and supporting accountability for core international crimes in line with European and international standards while fostering a holistic transitional justice approach.

Under Result 1.7.3, “Penitentiary and probation systems are strengthened in line with European standards”, the Programme supports improvements to policy and regulatory frameworks, professional capacity, institutional arrangements and rehabilitative interventions. Specialised psychological and training expertise is required to strengthen psychological services (1.7.3.1), develop and improve correctional and probation programmes (1.7.3.5), and build the capacity of penitentiary and probation professionals through training, mentoring and supervision (1.7.3.2). Specific assignments and deliverables will be determined in consultation with beneficiaries and in accordance with Programme priorities.

III. Objectives and desired results

1) General objective

To strengthen psychological services, rehabilitation interventions and professional training in the penitentiary and probation systems through programme development, methodological support, training and supervision.

2) Specific objectives

●Consult probation psychologists and regional stakeholders to identify methodological gaps and professional development needs.

●	Review the regulatory and methodological framework for probation psychological services and prepare recommendations.

●	Review, revise and develop priority probation and correctional programmes and accompanying manuals and materials.

●	Develop and adapt professional training curricula, methodological materials and, as assigned, content for a priority online course.

●	Deliver training and Training of Trainers sessions on psychological and motivational counselling, rehabilitation, behaviour change, vulnerable groups, staff support and trainer skills.

●	Provide mentoring, supervision and methodological consultations to psychologists and mentor-trainers.

●	Support preparation and staff training for piloting a revised probation/correctional programmes, including practical materials and feedback collection.

3) Anticipated results

●Psychological service needs and methodological gaps are documented.

●	Priority correctional and probation programmes and materials are improved.

●	Probation and penitentiary staff gain practical knowledge and skills through training and supervision.

●	Beneficiaries have improved guidance for professional psychological practice..

IV. Description of the assignment

1) Planned activities

The experts shall undertake the following activities in consultation with beneficiaries and under the supervision of designated Programme representatives. Specific priorities and tasks will be agreed through individual assignments over the contract period:

- Consult probation psychologists and regional stakeholders to identify methodological gaps and professional development needs.

- Review the regulatory and methodological framework for probation psychological services and prepare recommendations.

- Review, revise and develop priority probation and correctional programmes and accompanying manuals and materials.

- Develop and adapt professional training curricula, methodological materials and, as assigned, content for a priority online course.

- Deliver training and Training of Trainers sessions on psychological and motivational counselling, rehabilitation, behaviour change, vulnerable groups, staff support and trainer skills.

- Provide mentoring, supervision and methodological consultations to psychologists and mentor-trainers.

- Support preparation and staff training for piloting a revised probation programme, including practical materials and feedback collection.

The assignment may be delivered through a combination of on-site and remote work, subject to the approved work plan and contractual arrangements.

2) Anticipated deliverables

Deliverables:

D1. Assessment of psychological services and needs. Consultation summary and recommendations on psychological service.

D2. Revised programme and methodological package. Revised probation or correctional programme components, facilitator guidance and participant materials as assigned.

D3. Training package. Training agenda, presentation, exercises, participant materials and pre-/post-training assessment instruments.

D4. Delivery and supervision evidence. Training attendance lists, results of pre-/post-assessment, mentoring or supervision summaries and recommendations.

D5. Pilot support and final report. Materials supporting agreed programme piloting and analytical report on implementation, lessons and further improvements.

3) Consultation

Experts shall work under the overall supervision of the National Key Expert on Penitentiary Reform and Pillar 1 Lead.

The expert shall work under the overall supervision of PravoJustice4EU Programme management and the relevant thematic lead, in consultation with the National Key Expert on Penitentiary Reform, other Programme experts and designated beneficiary representatives. Draft outputs shall be submitted for review and revised in response to consolidated feedback.

Experts shall promptly communicate any potential conflict of interest, confidentiality concern or other circumstance that may affect the performance of the assignment.

4) Implementation period

Start date: January 2027

End date: June 2030

Effective duration of the assignment: 42 months

5) Place of performance

Remotely

V.  Required expertise and profile

1) Number of experts per assignment: 2

2) Profile of the designated expert responsible for contract execution

A. Qualifications and skills:

- Advanced university degree (Master’s degree or PhD) in psychology.

- Strong psychological counselling, rehabilitation and behaviour-change expertise.

- Excellent facilitation, ToT, training design and methodological writing skills.

- Ability to mentor and supervise practising psychologists.

- Fluency in Ukrainian is required; English is an asset.

- B. General professional experience

●	At least 5 years of professional experience in psychology, counselling, rehabilitation or professional training.

●	Experience developing and delivering professional training and methodological materials.

●	Experience developing probation and/or correctional programmes

C. Specific professional experience

●	Practical cooperation and psychological work in both penitentiary and probation systems.

●	Documented authorship or co-authorship of probation and/or correctional programmes.

●	Experience with professional training, ToT, mentorship or supervision of psychologists.

●	Experience with motivational counselling, vulnerable groups, behavioural change or psychological support to staff.

●	Previous experience under Pravo-Justice or another EU-funded or internationally supported justice-sector reform programme is an asset.

The two experts may bring complementary specialisations within the common profile and will receive separate assignments and individual contracts.

VI. Assignment reports

The experts shall provide periodic activity and progress reporting in accordance with the contractual modality and Program procedures. This may include monthly or periodic progress reports and timesheets, as applicable, summarizing work performed, tasks completed, documents prepared or reviewed, meetings and consultations attended, outputs produced, issues encountered and proposed next steps. All substantive deliverables shall be submitted to Expertise France for review and acceptance, and consolidated comments shall be addressed within the agreed timeframe.

VII. Monitoring-evaluation

Performance indicators

| Deliverables | Immediate effects | Intermediate effects | Verification sources |
| --- | --- | --- | --- |
| Assessment of psychological services and needs | Practical gaps and priority needs in psychological services are documented through consultations and analysis. | Beneficiaries can prioritise improvements to psychological practice and relevant guidance. | Needs assessment; consultation notes; recommendations; beneficiary feedback. |
| Correctional and probation programmes and materials | Selected programmes and supporting materials are reviewed, drafted or revised with practical implementation guidance. | Institutions have stronger programme resources to support rehabilitation and behaviour change. | Draft/revised programmes; manuals; review comments; acceptance records. |
| Training curricula and learning materials | Relevant staff receive structured curricula, modules and materials tailored to identified professional needs. | Training provision becomes more consistent and can be replicated by institutional trainers. | Curricula; training modules; presentations; online-course materials where assigned. |
| Training, ToT, mentoring and supervision | Participants receive practical instruction, feedback and supervision on agreed professional topics. | Psychologists and mentor-trainers are better equipped to apply and transfer skills in practice. | Training agendas; List participants; evaluation or pre/post-test results where used; supervision notes. |
| Pilot support and consolidated recommendations | Selected pilot sites receive preparation, materials and documented feedback; follow-up recommendations are consolidated. | Beneficiaries can refine programme implementation and plan further rollout based on pilot learning. | Pilot materials; feedback summaries; final recommendations; beneficiary acceptance. |

VIII. Practical information

The experts shall comply with all applicable Expertise France contractual, administrative, security, confidentiality, data-protection, ethics, conflict-of-interest and visibility requirements. Participation in travel, events or activities outside the normal place of performance shall be subject to prior approval and applicable Program procedures.

The required working language is Ukrainian; English is an asset. Deliverables shall be prepared in Ukrainian. Working days include preparation, consultations, drafting, training delivery, mentoring, supervision and revision of outputs. Work may be remotely, subject to Programme approval.

IX. Evaluation Criteria

Criterion 1: Financial offer / Price (rate per day) – 30 points

The financial score will cover the comparison of the financial offers of all candidates having submitted a conforming proposal.

Criterion 2: Technical offer – 70 points

Technical evaluation (desk review and/or interview based):

| Sub-criterion 1: Education - University degree in Psychology from an accredited university – 5 points. - Master's degree or higher qualification in Psychology – 5 points. | 10 |
| --- | --- |
| Sub-criterion 2: Experience - At least 5 years of professional experience in psychology, psychological rehabilitation, correctional interventions or professional training – 10 points. - Demonstrated practical experience providing psychological services, developing psychological interventions or supporting rehabilitation activities within both penitentiary and probation systems – 10 points. - Demonstrated authorship or co-authorship of probation and/or correctional programmes for persons in conflict with the law – 5 points. - Experience in developing training programmes and methodological materials, delivering trainings or Training of Trainers (ToT), and providing mentoring or supervision to professionals – 5 points. - Previous experience under Pravo-Justice or another EU-funded or internationally supported justice-sector reform programme in Ukraine – 5 points. | 35 |
| Sub-criterion 3: Technical Knowledge & Skills - Understanding of the assignment, with all relevant components of the ToR identified and addressed – 22 points: - Excellent – 22 points - Good – 20 points - Satisfactory – 15 points - Poor – 9 points - Very poor – 2 points - Full professional proficiency in written and spoken Ukrainian – 2 points. - Working knowledge of English – 1 point. | 25 |
| Total | 70 |

Each technical offer, deemed to be technically conforming, will be attributed a technical score.  By adding up the weighted scores obtained for each sub-criterion.

Where the contracting modality provides for a financial offer, the weighting between the technical and financial evaluation shall be specified in the call for applications.

X.  Submission Details

The candidate should provide:

•  Updated CV demonstrating compliance with the required expertise and profile.

•  Financial offer / proposed daily rate, where applicable to the contracting modality.

•  The selected candidate will be requested to provide additional supporting documentation requested for evaluation, due diligence, or contracting purposes.